## query (17)
Issue ID | Question | Owner | Issue Status | AHCCCS Response | Sandata Response/Clarifications (if applicable)
1 | Will AHCCCS require the provider to authorize and do EVV for services where we are secondary? What happens if the provider fails to get authorization or do EVV because they thought the member had other primary insurance? | Dean, Keeley A | Active
2 | What if the member is unable to perform the tasks that were outlined in the data? What is the alternative approach? | Dean, Keeley A | Resolved | AHCCCS is developing policy around visit verification. Also, if the member refuses to verify a visit, the provider can choose a reason code that the member refused to verify or accept services. We need you to re-phrase the question, unsure what is being asked.
3 | DDD Claims submission - what does this look like? | Hargens, Brad | Resolved | Answer too long - see AHCCCS HP Questions attachment. Mercy Care is meeting with DDD. Any further questions will be determined thereafter.
4 | How to address administrative burden on provider, especially BH OP? | Steving, Karrie | Resolved | AHCCCS is having internal discussions with BH providers & Sandata to reach a solution. Yes we are working with a small group of BH providers. We have paused that work due to COVID-19 response efforts and plan to resume in May. Update 7/20 - Meetings will resume in August.
5 | What are the ongoing costs and is that expected to be at providers expense? | Hargens, Brad | Active - Has this one been resolved? | Answered in question above. (20) AHCCCS has indicated they will support initial costs. MCO is wondering if providers will receive additional support for any ongoing costs to maintain the Sandata system access? Providers may need to hire an admin tp perform adminstrative functions to support EVV tasks, would this type of cost be covered by AHCCCS? In addition to AHCCCS providing for the cost of the Sandata system and devices, we have also utilized the DAP to support providers transition to and use of the system while also incentivizing behavior to support successful implementation of EVV.
6 | Please clarify how EVV will work for members with guardians. | Brown, Leona M | Active | Please provide a more specific question, this is too broad and not sure where the question is leading. Will members be able to complete an EVV without the presence of their guardian? What is the criteria for age? Can minor sign for themselves (i.e. TAY services)? When will policy be defined? AHCCCS is addressing this the EVV policy regarding verification and designees including minimum age requirements. Yes, members can get a service with EVV verification without the guardian being present. The guardian (or designee) can approve service delivery through a portal if they can't do it at the point of care.
7 | AHCCCS has made some accommodations for the verification process for members with physical or cognitive disabilities that prevent them from verifying receipt of service. What will the process be if the alternative methods do not work for the member? | Brown, Leona M | Resolved | First, there are multiple modalities for EVV and the member has the choice in what option to choose. Second, each modaility has a few different ways for the member to verify service delivery. Lastly, if those options are exhausted, the member can appoint someone to verify service delivery on their behalf.
8 | What denial message would be utilized for the claims for these services which do not have an EVV Service confirmation? And are these to be considered for claims dispute? | Hargens, Brad | Active | Initially AHCCCS asks that these situations not be denied for a minimum of 60-90 days and instead be treated as a "soft"/"warning" type editing and used to validate processing EVV data as well as to educate providers. AHCCCS will work on creating proposed messaging for rejects to providers. After the soft go-live, if/when these issues persist, MCOs will find value in having denial and claims dispute messaging to be clear. Remit & 835 comments must be HIPPAA compliant. CARC/RARC will need to be updated prior to implementing.
9 | Is there a limit on the frequency or length of time of the EVV service confirmations? For example, Can a provider build an EVVSC from 1/1/2020 - 1/1/2021 for 1,000 units per member? What precludes provider from doing this? | Dean, Keeley A | Active | AHCCCS will work with the MCOs to address this during the provider training on the service confirmation portal. To -date AHCCCS has communicated that the provider needs to provide an appropriate estimation based upon the treatment plan. We may need to consider monitoring for this issue.
10 | How will AHCCCS handle and/or the MCOs be expected to handle corrective action for providers who do not report EVV Service confirmations? MC currently has a dedicated staff who manages this for ALTCS which includes regular outreach and CAPs. | Cunningham, James M | Resolved | AHCCCS would like to work in collaboration with the MCOs to develop some metrics that support an overall determination as to whether or not a provider is in compliance with EVV. We can also use the DAP as a way to incentivize behavior that we want to see that leads to overall compliance
11 | Please clearly outline how AHCCCS expects MCOs to manage claim denials for EVV Service confirmations? | Monte, John P | Active | Please clarify is this encompassed in your question 31?​ This question encompasses the process flow of claims disputes and managing denials between Sandata, AHCCCS and the MCO. 5/13 updated response, AHCCCS will ask Sandata to add this as an agenda item for a future technical meeting , request sent to Sandata to add to future meeting.
12 | Mercy Care is requesting AHCCCS EVV Communication plan to providers and members. | Munn, Laurie | Active | AHCCCS has scheduled a call for 3/3/2020 to discuss the EVV Communication Plan. ​ See response to line 10.
13 | What edits, if any, will be applied by Sandata to the auth start date? May MCOs submit past auth start dates? | Bangert, Sean | Resolved | Authorization records can only be updated or changed by the source system.​
14 | Does 'segment: authorization limit' note pertain to 'authorizationserviceID'? | Bangert, Sean | Active | Response 5/13 - Sandata: From AZ Auth Addendum "Segment: AuthorizationLimit- This section is REQUIRED for all data elements marked as required. If AuthorizationLimitType = N the conditional data elements are not required." AuthorizationServiceID = Required.
15 | Clarify how provider goes back to enter service confirmations and scheduling for past dates? (i.e. services that have already occurred). | Bangert, Sean | Resolved | The AHCCCS hosted EVV Services Portal will allow for both retroactive and prospective entry.
16 | Does AHCCCS intend to use units or counts of units for non-PA services? | Hargens, Brad | Resolved - Please see question 41 | Please clarify the question, providers will enter the actual units of service they will (or if retroactively updated did) provide in the AHCCCS hosted EVV Services Portal.
17 | How will authorization amount be captured for per diem codes? (7 - AuthorizationAmountType) | Bangert, Sean | Active - Has this one been resolved? | Will hold mapping exercise to address rules for per diem. 2/27 Currently all service code in scope for AZ EVV program and designated with a 15-minute rounding rule to calculate billing units. Mercy Care is not clear on how to calculate billing units for per diem codes, will you please specifically address the values for those codes?
18 | When claim is denied for no EVV and provider submits EVVSC for a past date, would this then require the plan to do a retro auth? Current process is provider receives denied claim for no auth and then disputes it and dispute is reviewed. Does the provider then resubmit the claim? How do we know when updates are made to EVVSC? Do we submit the claim back to Sandata once we know the EVVSC has been submitted retroactively? | Payan, Vickie M | Active | Yes, a retroactive PA or portal entry is applicable is expected. 5/13 updated response, If denied the provider should resubmit their claim and normally processing should send that resubmission back to Sandata for Claims Validation.
19 | Can Mercy Care ignore units for services that are not prior authorized? | Bangert, Sean | Active | Please clarify the quesiton, so you mean ignore the units the provider indicates they will (or did) provide in the portal? Why would this be necessary? Please see claims scenario. - Mercy Care would like to request a meeting to discuss claims scenario. 5/13 updated response, Would Mercy Care prefer to review this in the weekly group technical meeting with all MCO's and Sandata or in a 1-1 meeting?
20 | Mercy Care does not ask for medical necessity date today and is exploring opportunities to implement prior to EVV go-live date. When is Mercy Care allowed to begin addressing this change with providers? | Dean, Keeley A | Resolved | AHCCCS is currently developing some guidance for MCOs and providers. We plan to review with MCOs before making it final. That said, AHCCCS will work with MCOs to educate providers. We plan to incorporate this into the provider training and would prefer to work with MCOs to collaborate on training efforts. A meeting has been scheduled for July 30th.
21 | Mercy Care is working on a tool for providers to navigate where to send an EVV (PA vs AHCCCS Portal) by LOB. Does AHCCCS intend to create a reference tool? If so, by when? Will AHCCCS consider having a master grid with all HP submission details combined? | Dean, Keeley A | Resolved | Yes, AHCCCS will create a user guide for this portal. This should be drafted by sometime in late May or June. Are you suggesting that AHCCCS include on its site a centralized who authorizes what by plan? With many exceptions this may be difficult to express and maintain on an ongoing basis, would it be acceptable to provide a link to this information for each plan? Suggestion is for MCOs to collaborate to determine how to streamline this information into a consistent message. 5/13 updated response, agreed. Please let us know what we can do to facilitate and/or participate in this process.
22 | If provider submits a EVVSC but fails to secure the necessary PA from the MCO and appeals the claim denial and cites that a EVVSC was received, is there any expectation from AHCCCS for the MCO to accept the appeal based on the EVVSC being secured? | Hargens, Brad | Resolved | Please clarify the quesiton, are you refering to PA or service. Mercy Care's claim system will effectively deny these claims.
23 | MCOs may see an increase in provider appeals for retroactive EVV. Who would be responsible for that? The MCO or Sandata? What if a provider disputes a verification attempt with Sandata? | Vargas, David | Active | AHCCCS will ask Sandata to add this as an agenda item for a future technical meeting. 5/13 updated response, request sent to Sandata to add to future meeting. Sandata initial response: If a Provider states that they have an EVV visit that satisfies the Claims Validation submission we will investigate to determine if there is an issue with the logic.
24 | When will Mercy Care recieve additional information re: the EVV Communication plan at AHCCCS level? When will small workgroup commence? When will deck that was previously presented be distributed? | Munn, Laurie | Resolved | We will be engaging the MCOs on the timeline very soon which will include updates on the communication plans. A meeting is currently being scheduled.
25 | Has AHCCCS and Sandata been able to determine the matching rules for claims units? If so, what are the details? If not, when will this information be provided to Mercy Care? | Bangert, Sean | Active
26 | What service codes are impacted by the Member Support workflow and after hours requirements? | Hargens, Brad | Active | We are currently working on this an planning to share this with MCOs within the next week or so for input and discussion.
27 | For those services codes where Mercy Care and DDD have the same or different authorization/confirmation requirements for DDD members, how will these be reconciled through Sandata to ensure EVV is applied to the appropriate claims or tied back to the appropriate payer? (Please see grid provided by Mercy Care) | Dean, Keeley A | Active
28 | We have identified authorizations that meet the specified provider type, place of service, and service code but contain a modifier that is not listed in the addendum. For example, when an authorization has a HCPCS code of S5125 (attendant care) but with a modifier of U7 (agency with choice, not listed in the addendum) should we be including this record in our authorization file? If so, do we include this modifier on the record? | Wojciehowski, John B | Active | Please confirm if this is still an outstanding issue.
29 | As a follow up, might there be any documentation on the Aggregator? Based on the workflow and as you explained, MCO will have visibility into this tool so we can view what providers have submitted. What exactly will MCO’s be able to do in the Aggregator? Is it view only? It not clear what Health plans should do with the information within the Aggregator? Scenarios: If the provider is using an alternate EVV and sending directly to Sandata, and the Service requires an authorization from the Health plan, how will those request be handled? | Health Choice | Active | Yes, Aggregator access is read only into all visit data generated by Alt EVV vendors and Sandata EVV. In the scenario of Alt EVV, the vendor should ensure that an authorization is place prior to allowing that service to be performed.
30 | When you say Vendor, are you referencing the MCO’s/Health plans or the provider agency? Also, Can you help me understand the comment “ensure that an authorization is in place prior to allowing that service to be performed.” How does that work if the provider submits through the Alternate EVV as a Self-Confirmation (authorization). If the service requires an authorization from the health plan before the services can be performed, yet, the provider submits through the alternate EVV system as a self-reported authorization, what would keep the provider from performing the service? | Health Choice | Active | (SANDATA): In this scenario, I am referencing the alternate EVV vendor that an agency has chosen to use. In other words, they do not want to use the state-provided, Sandata EVV option. (SANDATA): Let’s bring this one up to Lori/AHCCCS as I’m not sure of the solution here.
31 | We are requesting clarification on the comment “ensure that an authorization is in place prior to allowing that service to be performed.” How does that work if the provider submits through the Alternate EVV as a Self-Confirmation (authorization). If the service requires an authorization from the health plan before the services can be performed, yet, the provider submits through the alternate EVV system as a self-reported authorization, what would keep the provider from performing the service | Health Choice | Active
32 | What are the expectation for providers that are in a different network (Not AHCCCS/Medicaid provider), Are these providers expected to submit EVV Self Confirmation so that MCO’s can validate claims against? | Health Choice | Active
33 | Will Sandata be expecting to receive claims by Date of Service or Date Received? | Health Choice | Active
34 | Are there any changes to claim turnaround expectations, now with the introduction of claims validation through Sandata? | Health Choice | Active
35 | Mercy Care is requesting direction in terms of the process and timing of denials for service units that do not have a corresponding service confirmation on record at San Data. To assist in the conversation, we are using an actual claims example. For this scenario, the services do not require prior authorization by Mercy Care and therefore only a service confirmation record is submitted/created by the provider prior to performing the services. Within the service confirmation that the provider submits to the AHCCCS/San Data system is for dates of services 1/1/2020-1/8/2020 and is for 60 units or 4 hours of Attendant Care Services. The claim is received by Mercy Care for this time-period, but the total units billed are for 64 units. Per the conversation between with San Data/AHCCCS/Mercy Care on 4/22/2020, upon submission of the pre-payment claims file transaction the claim line details would be reviewed against service confirmation data and the 4 additional units would be identified and Mercy Care under the current model will receive notification via the claims response file transaction that the ENTIRE claim should be denied as no service confirmation is on file with San Data for 4 additional units. Mercy Care recommends service units NOT be considered in the EVV Claims Validation process and the MatchingRule for the Arizona configuration be set to ‘ExcludeUnits’. Health plans would continue examination of the service units through claims adjudication and interrogate this value from prior authorization records. This relatively minor configuration change would eliminate significant development effort at the health plans. The concerns Mercy Care has with a complete entire claim denial process are the burden this will place on both the provider and health plans. If Health Plans were to continue with their current procedures where only a limited number of services in scope for EVV require prior authorization, a provider will receive a denial for all service lines although a service confirmation is on record, just not for all the units. The current approach used by the MCO for prior-authorized services would be a partial denial. Some specific concerns with the full denial approach are: 1. Increased Call Volume – Providers will be confused with a full denial although a service confirmation was submitted. Additionally, who would be handling the phone calls from providers on these denials, is it the MCO or other agency (San Data mentioned it would not be them). 2. Impact to Provider Revenue Cycles – Providers will not receive reimbursement for entire claim, and actions to resolve would be submission of retro-updated service confirmation by provider to San Data, re-submission of claims to health plan and payment cycle to be completed, elongating the revenue cycle in best case scenarios to nearly a month. Concern would be that the providers will request advances to cover expenses, and the increase in administrative overhead for both MCO and Providers. 3. Increased Claim Costs – Each MCO pays their clearinghouses on a per claim submission basis and an increased volume of resubmissions will drive this cost up. Some specific concerns with the partial denial approach are the same, but with a lesser impact to the Provider’s Revenue Cycle. Important to note, these services in scope do NOT require prior-authorization currently at the MCO so providers are not accustomed to receiving denials: 1. Increased Call Volume – Providers will be confused with a partial denial although a service confirmation was submitted. Additionally, who would be handling the phone calls from providers on these denials, is it the MCO or other agency (San Data mentioned it would not be them). 2. Impact to Provider Revenue Cycles – Providers will not receive reimbursement for entire claim, and actions to resolve would be submission of retro-updated service confirmation by provider to San Data, re-submission of claims to health plan and payment cycle to be completed, elongating the revenue cycle in best case scenarios to nearly a month. Concern would be that the providers will request advances to cover expenses, and the increase in administrative overhead for both MCO and Providers. 3. Increased Claim Costs – Each MCO pays their clearinghouses on a per claim submission basis and an increased volume of resubmissions will drive this cost up. Additional item that we would appreciate guidance from AHCCCS on is regarding services that require Prior-Authorization at the MCO. If a provider submits a service confirmation to San Data but fails to secure the necessary Prior-Authorization from the MCO and appeals the claim denial and cites that a service confirmation was received, is there any expectation from AHCCCS for the MCO to accept the appeal based on the service-confirmation being secured? |  | Active