## Summary
SOLICITATION # YH19-0028
AHCCCS WORKS PORTAL
ATTACHMENT A: PRICING PROPOSAL WORKSHEET
OFFEROR NAME:
Total System Cost Summaries
This will be the Total Cost Summaries from each of the Tabs in this spreadsheet
Description | One Time Costs | Year 1 Costs
Software Costs | 0 | 0
Implementation Costs | 0 | na
| 0 | 0
Cost of Ownership: | 0

## Software
SOLICITATION # YH19-0028
AHCCCS WORKS PORTAL
SOFTWARE PRICING
Provide a line item for all software costs of the proposed solution (if applicable).
Description | Qty | Unit Cost | Total One Time Cost | Yearly Maintenance Cost
Subscription Pricing (if applicable) |  |  | 0 | 0
Hosting Fees (if applicable) |  |  | 0 | 0
License Fees (if applicable) |  |  | 0 | 0
Other |  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  | Total Cost: | 0 | 0

## Implementation
SOLICITATION # YH19-0028
AHCCCS WORKS PORTAL
IMPLEMENTATION PRICING
Provide a line item for all implementation costs. |  |  | Total Project Run
Description | COST | Duration (days)
Process Analysis and System Requirements | 0 | 30 | 30
System Design | 0 | 90 | 120
System Development | 0 | 90 | 210
State Integration Testing and Evaluation | 0 | 90 | 300
Implementation | 0 | 10 | 310
Go Live | 0 | 0 | 310
Post Implementation Support | 0 | 90 | 400
Other | 0
0
0
0
Total Cost: | 0
Implementation Costs shall include all travel.

## Implementation Deliverables
SOLICITATION # YH19-0028
AHCCCS Works Portal
IMPLEMENTATION DELIVERABLES
The primary project deliverable for Implementation will be a completed AHCCCS Works Portal that includes the following. Please complete all columns of this attachment and submit with response.
Deliverable | # of Staff & Titles | Hourly Rate | # of Hours
1. Business process analysis and system requirements document (Deliverable within 30 days from contract start date)
a. Baseline Review (includes Project Start-Up along with Administrative and Baseline Reviews)
b. System Security Assessment
c. Data/System Security Plan
d. Data Use/Exchange Interconnection Security Agreement
e. Risk Assessment Plan
f. Complete Privacy Impact Analysis (PIA), System Security Plan (SSP) and Information Security Risk Assessment (ISRA)
2. System Design (Deliverable 90 days from System Requirements Document Acceptance)
a. Interface Design/Control document.
b. Architecture walkthrough and requirements analysis
c. Database design
d. Detailed Design Review (includes Preliminary and Detailed Design Reviews)
e. Final Detailed Design Review
3. Development (Deliverable 90 days from Design Review Acceptance)
a. Portals, for state worker access, customer enrollment/registration and reporting
b. User training plan (knowledge transfer, desktop manuals, on-site training)
c. Contingency Plan/Recovery Plan
4. Testing and Evaluation (Deliverable 90 days from Design Review Acceptance)
a. Test plan for functional, integration, system, regression and user acceptance testing
b. Validation of test reporting
c. Error reporting and remediation planning for test stages
5. Implementation (Deliverable 10 days from Integrated Testing Acceptance)
a. Implementation/Roll out plan to include dashboard reporting.
b. Validated of production reports
c. Ongoing error reporting
d. SLA agreements
6. Post Implementation (Deliverable 90 days from Integrated Testing Acceptance)
a. Post implementation documentation delivery
b. Post implementation support/maintenance plan
c. Error reporting and remediation planning