## Summary
SOLICITATION # YH18-0033
PROVIDER MANAGEMENT SYSTEM
ATTACHMENT B: PRICING PROPOSAL WORKSHEET - Arizona
OFFEROR NAME: |  |  | Digital Harbor, Inc.
Total System Cost Summaries
This will be the Total Cost Summaries from each of the Tabs in this spreadsheet
Description | One Time Costs | Year 1 Costs | Year 2 Costs | Year 3 Costs | Year 4 Costs | Year 5 Costs
Software Costs | 0 | 3266000 | 3331320 | 3397946.4 | 3465905.328 | 3535223.4346
Implementation Costs | 2926000 | na | na | na | na | na
| 2926000 | 3266000 | 3331320 | 3397946.4 | 3465905.328 | 3535223.4346
5-year Cost of Ownership: | 19922395.1626

## Software
SOLICITATION # YH18-0033
PROVIDER MANAGEMENT SYSTEM
SOFTWARE PRICING
Provide a line item for all software costs of the proposed solution (if applicable).
Description | Qty | Unit Cost | Total One Time Cost | Year 1 Maintenance Cost | Year 2 Maintenance Cost | Year 3 Maintenance Cost | Year 4 Maintenance Cost | Year 5 Maintenance Cost
Subscription Pricing (if applicable) | 71000 | 46 | 0 | 3266000 | 3331320 | 3397946.4 | 3465905.328 | 3535223.4346
Hosting Fees (if applicable) |  |  | 0 | 0 | 0 | 0 | 0 | 0
License Fees (if applicable) |  |  | 0 | 0 | 0 | 0 | 0 | 0
Other |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Cost: | 0 | 3266000 | 3331320 | 3397946.4 | 3465905.328 | 3535223.4346
KYP SaaS offering is based on subscription and includes commercial data and software licenses, hardware, networking, Customer Support, and IT and data Operations Support

## Implementation
SOLICITATION # YH18-0033
PROVIDER MANAGEMENT SYSTEM
IMPLEMENTATION PRICING
Implementation is the time from contract execution through the CMS Certification Milestone as described in the MECL (https://www.medicaid.gov/medicaid/data-and-systems/mect/index.html)
Provide a line item for all implementation costs.
Description | Q4 SFY2018 | Q1 SFY 2019 | Q2 SFY 2019 | Q3 SFY 2019 | Q4 SFY 2019 | Q1 SFY 2020 | Total
Project Management | 79200 | 79200 | 79200 | 79200 | 39600 | 39600 | 396000
Configuration | 275000 | 275000 | 275000 | 0 | 0 | 0 | 825000
Interfaces | 110000 | 220000 | 220000 | 0 | 0 | 0 | 550000
Data Conversion |  | 110000 | 110000 | 0 | 0 | 0 | 220000
Testing |  | 165000 | 165000 | 0 | 0 | 0 | 330000
Training | 0 | 55000 | 55000 | 0 | 0 | 0 | 110000
Deployment/Installation | 0 | 82500 | 82500 | 0 | 0 | 0 | 165000
Post Implementation Support | 0 | 0 | 0 | 110000 | 0 | 0 | 110000
Documentation | 55000 | 55000 | 55000 | 55000 | 0 | 0 | 220000
Other | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Cost: | 519200 | 1041700 | 1041700 | 244200 | 39600 | 39600 | 2926000
Implementation Costs shall include all travel. Use the following assumptions for estimating travel:
*For Requirements Section of the Scope of Work: 1-2 trips for each State
*For Development: No travel should be assumed
*For Testing the System: 1 trip should be assumed for each State
*For Implementation of the System: 1-2 trips should be assumed for each State
*For Training: 1-2 trips should be assumed for each State
*The duration should be assumed to be 2-3 days per trip for each State

## Implementation Deliverables
SOLICITATION # YH18-0033
PROVIDER MANAGEMENT SYSTEM
IMPLEMENTATION DELIVERABLES
The primary project deliverable for Implementation will be a completed Provider Registration Package that includes the following. Please complete all columns of this attachment and submit with response.
Deliverable | Staff Titles | Hourly Rate | # of Hours | Proposed Timeline
1. Project Management (Weekly and on-going as defined) | Project Manager | 165 | 2500 | 600 Days
a. Weekly IT Planning Session involvement | Project Manager, Architect, Deployment Manager | 165
b. Develop milestone schedule. (weekly, monthly and quarterly) | Project Manager | 165
c. Contributions to the overall project plan maintained by AHCCCS/Med-QUEST | Project Manager | 165
2. Business process analysis and system requirements document (Deliverable within 30 days from contract implementation) | Product Manager, Business Analyst | 165 | 2000 | 60 days
a. Baseline Review (includes Project Start-Up along with Administrative and Baseline Reviews) | Product Manager, Business Analyst | 165
b. System Security Assessment | Security Manager | 165
c. Data/System Security Plan | Data Architect, Security Architect | 165
d. Data Use/Exchange Interconnection Security Agreement | Data Architect, Security Architect | 165
e. Risk Assessment Plan | Security Manager | 165
f. Complete Privacy Impact Analysis (PIA) | Security Manager | 165
3. System Design (Deliverable 60-90 days from contract implementation agreed upon between AHCCCS/Med-QUEST and Contractor) | System Architect | 165 | 1500 | 60 days
a. Interface Design/Control document. COTS to mainframe interface design. | System Architect | 165
b. Architecture walkthrough and requirements analysis | System Architect, Business Analyst | 165
c. Database design | Data Architect | 165
d. Detailed Design Review (includes Preliminary and Detailed Design Reviews) | System Architect, Business Analyst | 165
e. Final Detailed Design Review | System Architect, Business Analyst | 165
f. Data conversion analysis and conversion plan | Data Architect | 165
4. Development (Begin date NLT 120 days from contract implementation date) | Architect, Configuration Analyst, Software Engineer | 165 | 5000 | 120 days
a. Portals, for state worker access, Provider enrollment/registration and reporting | Business Analyst, Configuration Analyst | 165
b. User training plan (knowledge transfer, desktop manuals, on-site training) | Training Manager, Business Analyst | 165
c. Contingency Plan/Recovery Plan | Project Manager, Security Manager, DevOps Manager | 165
165
5. Testing and Evaluation (Begin Date NLT 160 days from contract implementation date) | QA Manager, Testers | 165 | 2000 | 60 days
a. Test plan for functional, integration, system, regression and user acceptance testing | Project Manager, QA Manager | 165
b. Validation of test reporting | Tester, Certification Manager | 165
c. Error reporting and remediation planning for test stages | Customer Support Manager, Testing Manger | 165
6. Implementation (Deliverable 10 days from Integrated Testing Acceptance) | DevOps Manager, Project Manger | 165
a. Implementation/Roll out plan to include dashboard reporting. | DevOps Manager, Project Manger | 165
b. Validated of production reports | DevOps Manager, Project Manger | 165
c. Ongoing error reporting | DevOps Manager, Project Manger | 165
d. SLA agreements | DevOps Manager, Project Manger | 165
7. Post Implementation (Deliverable 60 days from Integrated Testing Acceptance) |  |  | 2000 | 90 days
a. Post implementation plan for both AHCCCS/Med-Quest | Project Manager, Deployment Manager | 165
b. Post implementation documentation delivery | Business Analyst, Documentation Analyst | 165
c. Post implementation support/maintenance plan | Project Manager, Deployment Manager | 165
d. Error reporting and remediation planning | Project Manager | 165
8. IV&V Coordination and Reporting (This is an ongoing requirement from date of contraction implementation through System Certification by CMS. Targeted end date is December 2019) | Project Manager, Certification Manager | 165 | 2000 | 180 days
a. Timely response to all request from IV&V | Business Analyst, System Architect, Certification Manager | 165
b. Quarterly reporting | Certification Manager | 165
c. Milestone reporting | Certification Manager | 165