## Summary
SOLICITATION # YH18-0033
PROVIDER MANAGEMENT SYSTEM
ATTACHMENT B: PRICING PROPOSAL WORKSHEET
OFFEROR NAME: |  |  | MAXIMUS Human Services, Inc.
Total System Cost Summaries
This will be the Total Cost Summaries from each of the Tabs in this spreadsheet
Description | One Time Costs | Year 1 Costs | Year 2 Costs | Year 3 Costs | Year 4 Costs | Year 5 Costs
Software Costs | 1582511.8221 | 3631643.5825 | 2471618.5212 | 2262360.0859 | 2288671.1388 | 2030761.28
Implementation Costs | 5515578.9616 | na | na | na | na | na
| 7098090.7837 | 3631643.5825 | 2471618.5212 | 2262360.0859 | 2288671.1388 | 2030761.28
5-year Cost of Ownership: | 19783145.3922

## Software
SOLICITATION # YH18-0033
PROVIDER MANAGEMENT SYSTEM
SOFTWARE PRICING
MAXIMUS Human Services, Inc.
Provide a line item for all software costs of the proposed solution (if applicable).
Description | Qty | Unit Cost | Total One Time Cost | Year 1 Maintenance Cost | Year 2 Maintenance Cost | Year 3 Maintenance Cost | Year 4 Maintenance Cost | Year 5 Maintenance Cost
Subscription Pricing (if applicable) |  |  | 1581704.46 | 813035.2998 | 775947.1927 | 789403.368 | 803199.7923 | 521471.5238
Hosting Fees (if applicable) |  |  | 807.3621 | 276576.196 | 276576.196 | 276576.196 | 276576.196 | 276576.196
License Fees (if applicable) |  |  | 0 | 0 | 0 | 0 | 0 | 0
Other |  |  | 0 | 2542032.0867 | 1419095.1325 | 1196380.5219 | 1208895.1505 | 1232713.5602
|  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Cost: | 1582511.8221 | 3631643.5825 | 2471618.5212 | 2262360.0859 | 2288671.1388 | 2030761.28

## Implementation
SOLICITATION # YH18-0033
PROVIDER MANAGEMENT SYSTEM
IMPLEMENTATION PRICING | [5 empty] | MAXIMUS Human Services, Inc.
Implementation is the time from contract execution through the CMS Certification Milestone as described in the MECL (https://www.medicaid.gov/medicaid/data-and-systems/mect/index.html)
Provide a line item for all implementation costs.
Description | Q1 SFY 2019 | Q2 SFY 2019 | Q3 SFY 2019 | Q4 SFY 2019 | Q1 SFY 2020 | Q2 SFY 2020 | Total
Project Management | 44614.3844 | 142518.1723 | 142518.1723 | 151193.1915 | 68408.1517 | 0 | 549252.0721
Configuration | 155899.464 | 762746.6425 | 454708.9988 | 14440.782 | 31192.089 | 0 | 1418987.9763
Interfaces | 56763.0546 | 175659.784 | 134931.9032 | 14440.782 | 31192.089 | 0 | 412987.6128
Data Conversion | 49298.6017 | 157089.8439 | 129171.9312 | 14440.782 | 31192.089 | 0 | 381193.2479
Testing | 0 | 0 | 342556.9637 | 769483.3329 | 0 | 0 | 1112040.2967
Training | 0 | 62930.008 | 76621.9831 | 88237.5113 | 52805.2912 | 0 | 280594.7936
Deployment/Installation | 0 | 0 | 0 | 371241.1849 | 0 | 0 | 371241.1849
Post Implementation Support | 0 | 0 | 0 | 0 | 679488.9316 | 0 | 679488.9316
Documentation | 8733.8115 | 27899.6757 | 27899.6757 | 29597.9168 | 109674.146 | 105987.6201 | 309792.8458
Other | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Cost: | 315309.3162 | 1328844.1264 | 1308409.628 | 1453075.4833 | 1003952.7876 | 105987.6201 | 5515578.9616
Implementation Costs shall include all travel. Use the following assumptions for estimating travel:
*For Requirements Section of the Scope of Work: 1-2 trips for each State
*For Development: No travel should be assumed
*For Testing the System: 1 trip should be assumed for each State
*For Implementation of the System: 1-2 trips should be assumed for each State
*For Training: 1-2 trips should be assumed for each State
*The duration should be assumed to be 2-3 days per trip for each State

## Implementation Deliverables
SOLICITATION # YH18-0033
PROVIDER MANAGEMENT SYSTEM
IMPLEMENTATION DELIVERABLES
The primary project deliverable for Implementation will be a completed Provider Registration Package that includes the following. Please complete all columns of this attachment and submit with response. |  |  |  | MAXIMUS Human Services, Inc.
Deliverable | Staff Titles | Hourly Rate | # of Hours | Proposed Timeline
1. Project Management (Weekly and on-going as defined)
a. Weekly IT Planning Session involvement |  |  |  | Ongoing to 8/31/2019
a. Weekly IT Planning Session involvement | Project Manager | 172.3827 | 1091.16
a. Weekly IT Planning Session involvement | QA Analyst | 124.9449 | 375.2
a. Weekly IT Planning Session involvement | Business Lead | 154.5935 | 93.12
a. Weekly IT Planning Session involvement | Integration Lead | 142.7341 | 93.12
b. Develop milestone schedule. (weekly, monthly and quarterly) |  |  |  | Ongoing to 8/31/2019
b. Develop milestone schedule. (weekly, monthly and quarterly) | Project Manager | 172.3827 | 311.76
b. Develop milestone schedule. (weekly, monthly and quarterly) | QA Analyst | 124.9449 | 750.4
b. Develop milestone schedule. (weekly, monthly and quarterly) | Business Lead | 154.5935 | 31.04
b. Develop milestone schedule. (weekly, monthly and quarterly) | Integration Lead | 142.7341 | 31.04
c. Contributions to the overall project plan maintained by AHCCCS/Med-QUEST |  |  |  | Ongoing to 8/31/2019
c. Contributions to the overall project plan maintained by AHCCCS/Med-QUEST | Project Manager | 172.3827 | 155.88
c. Contributions to the overall project plan maintained by AHCCCS/Med-QUEST | QA Analyst | 124.9449 | 750.4
c. Contributions to the overall project plan maintained by AHCCCS/Med-QUEST | Business Lead | 154.5935 | 31.04
c. Contributions to the overall project plan maintained by AHCCCS/Med-QUEST | Integration Lead | 142.7341 | 31.04
2. Business process analysis and system requirements document (Deliverable within 30 days from contract implementation) |  |  |  | 2018-10-18
a. Baseline Review (includes Project Start-Up along with Administrative and Baseline Reviews) |  |  |  | 2018-09-24
a. Baseline Review (includes Project Start-Up along with Administrative and Baseline Reviews) | Business Lead | 154.5935 | 32.73
a. Baseline Review (includes Project Start-Up along with Administrative and Baseline Reviews) | Integration Lead | 142.7341 | 25.536
a. Baseline Review (includes Project Start-Up along with Administrative and Baseline Reviews) | Senior Developer | 132.0633 | 181.944
a. Baseline Review (includes Project Start-Up along with Administrative and Baseline Reviews) | Developer | 119.1926 | 302.4
a. Baseline Review (includes Project Start-Up along with Administrative and Baseline Reviews) | Arizona Lead | 130.8746 | 61.164
a. Baseline Review (includes Project Start-Up along with Administrative and Baseline Reviews) | BA | 83.4369 | 117
a. Baseline Review (includes Project Start-Up along with Administrative and Baseline Reviews) | Senior BA | 113.0855 | 91.08
a. Baseline Review (includes Project Start-Up along with Administrative and Baseline Reviews) | Hawaii Lead | 130.8746 | 61.164
a. Baseline Review (includes Project Start-Up along with Administrative and Baseline Reviews) | Solution Architect | 192.5438 | 36.425
a. Baseline Review (includes Project Start-Up along with Administrative and Baseline Reviews) | Server Engineer | 166.4435 | 14.7
a. Baseline Review (includes Project Start-Up along with Administrative and Baseline Reviews) | Senior Integration Engineer | 195.0565 | 0.915
a. Baseline Review (includes Project Start-Up along with Administrative and Baseline Reviews) | DBA | 174.878 | 4.572
a. Baseline Review (includes Project Start-Up along with Administrative and Baseline Reviews) | Application Systems Admin | 176.7521 | 6.84
a. Baseline Review (includes Project Start-Up along with Administrative and Baseline Reviews) | Configuration Manager | 176.7521 | 0.72
b. System Security Assessment |  |  |  | 2018-09-18
b. System Security Assessment | Business Lead | 154.5935 | 13.092
b. System Security Assessment | Integration Lead | 142.7341 | 19.152
b. System Security Assessment | Senior Developer | 132.0633 | 30.324
b. System Security Assessment | Developer | 119.1926 | 50.4
b. System Security Assessment | Arizona Lead | 130.8746 | 10.194
b. System Security Assessment | BA | 83.4369 | 19.5
b. System Security Assessment | Senior BA | 113.0855 | 15.18
b. System Security Assessment | Hawaii Lead | 130.8746 | 10.194
b. System Security Assessment | Solution Architect | 192.5438 | 14.57
b. System Security Assessment | Server Engineer | 166.4435 | 5.88
b. System Security Assessment | Senior Integration Engineer | 195.0565 | 1.1437
b. System Security Assessment | DBA | 174.878 | 5.715
b. System Security Assessment | Application Systems Admin | 176.7521 | 8.55
b. System Security Assessment | Security Lead | 154.5935 | 12.96
b. System Security Assessment | Configuration Manager | 176.7521 | 0.9
c. Data/System Security Plan |  |  |  | 2018-09-18
c. Data/System Security Plan | Business Lead | 154.5935 | 6.546
c. Data/System Security Plan | Integration Lead | 142.7341 | 6.384
c. Data/System Security Plan | Senior Developer | 132.0633 | 30.324
c. Data/System Security Plan | Developer | 119.1926 | 50.4
c. Data/System Security Plan | Arizona Lead | 130.8746 | 10.194
c. Data/System Security Plan | BA | 83.4369 | 19.5
c. Data/System Security Plan | Senior BA | 113.0855 | 15.18
c. Data/System Security Plan | Hawaii Lead | 130.8746 | 10.194
c. Data/System Security Plan | Solution Architect | 192.5438 | 7.285
c. Data/System Security Plan | Server Engineer | 166.4435 | 2.94
c. Data/System Security Plan | Senior Integration Engineer | 195.0565 | 1.1437
c. Data/System Security Plan | DBA | 174.878 | 5.715
c. Data/System Security Plan | Application Systems Admin | 176.7521 | 8.55
c. Data/System Security Plan | Security Lead | 154.5935 | 8.1
c. Data/System Security Plan | Configuration Manager | 176.7521 | 0.9
d. Data Use/Exchange Interconnection Security Agreement |  |  |  | 2018-09-18
d. Data Use/Exchange Interconnection Security Agreement | Business Lead | 154.5935 | 15.1
d. Data Use/Exchange Interconnection Security Agreement | Integration Lead | 142.7341 | 53.2
d. Data Use/Exchange Interconnection Security Agreement | Interface Lead | 136.8044 | 266
d. Data Use/Exchange Interconnection Security Agreement | Senior Developer | 132.0633 | 266
d. Data Use/Exchange Interconnection Security Agreement | Solution Architect | 192.5438 | 84.4167
d. Data Use/Exchange Interconnection Security Agreement | Senior Integration Engineer | 195.0565 | 7.625
d. Data Use/Exchange Interconnection Security Agreement | Application Systems Admin | 176.7521 | 11.4
d. Data Use/Exchange Interconnection Security Agreement | Security Lead | 154.5935 | 20.25
e. Risk Assessment Plan |  |  |  | 2018-09-20
e. Risk Assessment Plan | Business Lead | 154.5935 | 6.546
e. Risk Assessment Plan | Integration Lead | 142.7341 | 6.384
e. Risk Assessment Plan | Senior Developer | 132.0633 | 30.324
e. Risk Assessment Plan | Developer | 119.1926 | 50.4
e. Risk Assessment Plan | Arizona Lead | 130.8746 | 10.194
e. Risk Assessment Plan | BA | 83.4369 | 19.5
e. Risk Assessment Plan | Senior BA | 113.0855 | 15.18
e. Risk Assessment Plan | Hawaii Lead | 130.8746 | 10.194
e. Risk Assessment Plan | Solution Architect | 192.5438 | 7.285
e. Risk Assessment Plan | Server Engineer | 166.4435 | 2.94
e. Risk Assessment Plan | Senior Integration Engineer | 195.0565 | 0.915
e. Risk Assessment Plan | DBA | 174.878 | 4.572
e. Risk Assessment Plan | Application Systems Admin | 176.7521 | 6.84
e. Risk Assessment Plan | Security Lead | 154.5935 | 8.1
e. Risk Assessment Plan | Configuration Manager | 176.7521 | 0.72
f. Complete Privacy Impact Analysis (PIA) |  |  |  | 2018-09-18
f. Complete Privacy Impact Analysis (PIA) | Business Lead | 154.5935 | 6.546
f. Complete Privacy Impact Analysis (PIA) | Integration Lead | 142.7341 | 6.384
f. Complete Privacy Impact Analysis (PIA) | Senior Developer | 132.0633 | 30.324
f. Complete Privacy Impact Analysis (PIA) | Developer | 119.1926 | 50.4
f. Complete Privacy Impact Analysis (PIA) | Arizona Lead | 130.8746 | 10.194
f. Complete Privacy Impact Analysis (PIA) | BA | 83.4369 | 19.5
f. Complete Privacy Impact Analysis (PIA) | Senior BA | 113.0855 | 15.18
f. Complete Privacy Impact Analysis (PIA) | Hawaii Lead | 130.8746 | 10.194
f. Complete Privacy Impact Analysis (PIA) | Solution Architect | 192.5438 | 7.285
f. Complete Privacy Impact Analysis (PIA) | Server Engineer | 166.4435 | 2.94
f. Complete Privacy Impact Analysis (PIA) | Senior Integration Engineer | 195.0565 | 0.4575
f. Complete Privacy Impact Analysis (PIA) | DBA | 174.878 | 2.286
f. Complete Privacy Impact Analysis (PIA) | Application Systems Admin | 176.7521 | 3.42
f. Complete Privacy Impact Analysis (PIA) | Security Lead | 154.5935 | 3.24
f. Complete Privacy Impact Analysis (PIA) | Configuration Manager | 176.7521 | 0.36
3. System Design (Deliverable 60-90 days from contract implementation agreed upon between AHCCCS/Med-QUEST and Contractor) |  |  |  | 2018-12-03
a. Interface Design/Control document. COTS to mainframe interface design. |  |  |  | 2018-11-12
a. Interface Design/Control document. COTS to mainframe interface design. | Business Lead | 154.5935 | 45.3
a. Interface Design/Control document. COTS to mainframe interface design. | Integration Lead | 142.7341 | 159.6
a. Interface Design/Control document. COTS to mainframe interface design. | Interface Lead | 136.8044 | 798
a. Interface Design/Control document. COTS to mainframe interface design. | Senior Developer | 132.0633 | 798
a. Interface Design/Control document. COTS to mainframe interface design. | Solution Architect | 192.5438 | 253.25
a. Interface Design/Control document. COTS to mainframe interface design. | Senior Integration Engineer | 195.0565 | 22.875
a. Interface Design/Control document. COTS to mainframe interface design. | Application Systems Admin | 176.7521 | 34.2
a. Interface Design/Control document. COTS to mainframe interface design. | Security Lead | 154.5935 | 60.75
b. Architecture walkthrough and requirements analysis |  |  |  | 2018-10-29
b. Architecture walkthrough and requirements analysis | Business Lead | 154.5935 | 21.82
b. Architecture walkthrough and requirements analysis | Integration Lead | 142.7341 | 21.28
b. Architecture walkthrough and requirements analysis | Senior Developer | 132.0633 | 101.08
b. Architecture walkthrough and requirements analysis | Developer | 119.1926 | 168
b. Architecture walkthrough and requirements analysis | Arizona Lead | 130.8746 | 16.99
b. Architecture walkthrough and requirements analysis | Hawaii Lead | 130.8746 | 16.99
b. Architecture walkthrough and requirements analysis | Solution Architect | 192.5438 | 24.2833
b. Architecture walkthrough and requirements analysis | Server Engineer | 166.4435 | 24.5
b. Architecture walkthrough and requirements analysis | Senior Integration Engineer | 195.0565 | 3.8125
b. Architecture walkthrough and requirements analysis | DBA | 174.878 | 7.62
b. Architecture walkthrough and requirements analysis | Application Systems Admin | 176.7521 | 28.5
b. Architecture walkthrough and requirements analysis | Security Lead | 154.5935 | 8.1
b. Architecture walkthrough and requirements analysis | Configuration Manager | 176.7521 | 3
c. Database design |  |  |  | 2018-10-29
c. Database design | Business Lead | 154.5935 | 21.82
c. Database design | Integration Lead | 142.7341 | 21.28
c. Database design | Senior Developer | 132.0633 | 101.08
c. Database design | Developer | 119.1926 | 168
c. Database design | Arizona Lead | 130.8746 | 33.98
c. Database design | BA | 83.4369 | 65
c. Database design | Senior BA | 113.0855 | 50.6
c. Database design | Hawaii Lead | 130.8746 | 33.98
c. Database design | Solution Architect | 192.5438 | 24.2833
c. Database design | Senior Integration Engineer | 195.0565 | 1.525
c. Database design | DBA | 174.878 | 19.05
c. Database design | Security Lead | 154.5935 | 8.1
c. Database design | Configuration Manager | 176.7521 | 1.2
d. Detailed Design Review (includes Preliminary and Detailed Design Reviews) |  |  |  | 2018-11-21
d. Detailed Design Review (includes Preliminary and Detailed Design Reviews) | Business Lead | 154.5935 | 43.64
d. Detailed Design Review (includes Preliminary and Detailed Design Reviews) | Integration Lead | 142.7341 | 42.56
d. Detailed Design Review (includes Preliminary and Detailed Design Reviews) | Senior Developer | 132.0633 | 202.16
d. Detailed Design Review (includes Preliminary and Detailed Design Reviews) | Developer | 119.1926 | 336
d. Detailed Design Review (includes Preliminary and Detailed Design Reviews) | Arizona Lead | 130.8746 | 84.95
d. Detailed Design Review (includes Preliminary and Detailed Design Reviews) | BA | 83.4369 | 162.5
d. Detailed Design Review (includes Preliminary and Detailed Design Reviews) | Senior BA | 113.0855 | 126.5
d. Detailed Design Review (includes Preliminary and Detailed Design Reviews) | Hawaii Lead | 130.8746 | 84.95
d. Detailed Design Review (includes Preliminary and Detailed Design Reviews) | Solution Architect | 192.5438 | 48.5667
d. Detailed Design Review (includes Preliminary and Detailed Design Reviews) | Server Engineer | 166.4435 | 12.25
d. Detailed Design Review (includes Preliminary and Detailed Design Reviews) | Senior Integration Engineer | 195.0565 | 1.525
d. Detailed Design Review (includes Preliminary and Detailed Design Reviews) | DBA | 174.878 | 7.62
d. Detailed Design Review (includes Preliminary and Detailed Design Reviews) | Application Systems Admin | 176.7521 | 14.25
d. Detailed Design Review (includes Preliminary and Detailed Design Reviews) | Security Lead | 154.5935 | 8.1
d. Detailed Design Review (includes Preliminary and Detailed Design Reviews) | Configuration Manager | 176.7521 | 1.2
e. Final Detailed Design Review |  |  |  | 2018-11-21
e. Final Detailed Design Review | Business Lead | 154.5935 | 21.82
e. Final Detailed Design Review | Integration Lead | 142.7341 | 21.28
e. Final Detailed Design Review | Senior Developer | 132.0633 | 101.08
e. Final Detailed Design Review | Developer | 119.1926 | 168
e. Final Detailed Design Review | Arizona Lead | 130.8746 | 33.98
e. Final Detailed Design Review | BA | 83.4369 | 97.5
e. Final Detailed Design Review | Senior BA | 113.0855 | 75.9
e. Final Detailed Design Review | Hawaii Lead | 130.8746 | 33.98
e. Final Detailed Design Review | Solution Architect | 192.5438 | 24.2833
e. Final Detailed Design Review | Server Engineer | 166.4435 | 12.25
e. Final Detailed Design Review | Senior Integration Engineer | 195.0565 | 0.7625
e. Final Detailed Design Review | DBA | 174.878 | 3.81
e. Final Detailed Design Review | Application Systems Admin | 176.7521 | 14.25
e. Final Detailed Design Review | Security Lead | 154.5935 | 8.1
e. Final Detailed Design Review | Configuration Manager | 176.7521 | 0.6
f. Data conversion analysis and conversion plan |  |  |  | 2018-11-19
f. Data conversion analysis and conversion plan | Business Lead | 154.5935 | 60.4
f. Data conversion analysis and conversion plan | Integration Lead | 142.7341 | 212.8
f. Data conversion analysis and conversion plan | Conversion Lead | 136.8044 | 1064
f. Data conversion analysis and conversion plan | Developer | 119.1926 | 1064
f. Data conversion analysis and conversion plan | Solution Architect | 192.5438 | 337.6667
f. Data conversion analysis and conversion plan | Application Systems Admin | 176.7521 | 45.6
4. Development (Begin date NLT 120 days from contract implementation date) |  |  |  | 2019-02-27
a. Portals, for state worker access, Provider enrollment/registration and reporting |  |  |  | 2019-02-27
a. Portals, for state worker access, Provider enrollment/registration and reporting | Business Lead | 154.5935 | 261.84
a. Portals, for state worker access, Provider enrollment/registration and reporting | Integration Lead | 142.7341 | 255.36
a. Portals, for state worker access, Provider enrollment/registration and reporting | Senior Developer | 132.0633 | 1212.96
a. Portals, for state worker access, Provider enrollment/registration and reporting | Developer | 119.1926 | 2016
a. Portals, for state worker access, Provider enrollment/registration and reporting | Arizona Lead | 130.8746 | 407.76
a. Portals, for state worker access, Provider enrollment/registration and reporting | BA | 83.4369 | 780
a. Portals, for state worker access, Provider enrollment/registration and reporting | Senior BA | 113.0855 | 607.2
a. Portals, for state worker access, Provider enrollment/registration and reporting | Hawaii Lead | 130.8746 | 407.76
a. Portals, for state worker access, Provider enrollment/registration and reporting | Solution Architect | 192.5438 | 291.4
a. Portals, for state worker access, Provider enrollment/registration and reporting | Server Engineer | 166.4435 | 117.6
a. Portals, for state worker access, Provider enrollment/registration and reporting | Senior Integration Engineer | 195.0565 | 18.3
a. Portals, for state worker access, Provider enrollment/registration and reporting | DBA | 174.878 | 91.44
a. Portals, for state worker access, Provider enrollment/registration and reporting | Application Systems Admin | 176.7521 | 136.8
a. Portals, for state worker access, Provider enrollment/registration and reporting | Security Lead | 154.5935 | 16.2
a. Portals, for state worker access, Provider enrollment/registration and reporting | Configuration Manager | 176.7521 | 14.4
b. User training plan (knowledge transfer, desktop manuals, on-site training) |  |  |  | 2019-05-03
b. User training plan (knowledge transfer, desktop manuals, on-site training) | Business Lead | 154.5935 | 117.1
b. User training plan (knowledge transfer, desktop manuals, on-site training) | Trainer | 136.8044 | 1732
b. User training plan (knowledge transfer, desktop manuals, on-site training) | Arizona Lead | 130.8746 | 97.6
b. User training plan (knowledge transfer, desktop manuals, on-site training) | Hawaii Lead | 130.8746 | 97.6
c. Contingency Plan/Recovery Plan |  |  |  | 2019-02-12
c. Contingency Plan/Recovery Plan | Business Lead | 154.5935 | 6
c. Contingency Plan/Recovery Plan | Integration Lead | 142.7341 | 12
c. Contingency Plan/Recovery Plan | Interface Lead | 136.8044 | 15
c. Contingency Plan/Recovery Plan | Senior Developer | 132.0633 | 43.5
c. Contingency Plan/Recovery Plan | Conversion Lead | 136.8044 | 15
c. Contingency Plan/Recovery Plan | Developer | 119.1926 | 70
c. Contingency Plan/Recovery Plan | Arizona Lead | 130.8746 | 13.5
c. Contingency Plan/Recovery Plan | BA | 83.4369 | 30
c. Contingency Plan/Recovery Plan | Senior BA | 113.0855 | 30
c. Contingency Plan/Recovery Plan | Hawaii Lead | 130.8746 | 13.5
c. Contingency Plan/Recovery Plan | Solution Architect | 192.5438 | 7.5
c. Contingency Plan/Recovery Plan | Server Engineer | 166.4435 | 9.8
c. Contingency Plan/Recovery Plan | BC/DR Analyst | 132.9077 | 2
c. Contingency Plan/Recovery Plan | Senior Integration Engineer | 195.0565 | 3.05
c. Contingency Plan/Recovery Plan | DBA | 174.878 | 5.08
c. Contingency Plan/Recovery Plan | Application Systems Admin | 176.7521 | 6.84
c. Contingency Plan/Recovery Plan | Security Lead | 154.5935 | 2.7
c. Contingency Plan/Recovery Plan | Configuration Manager | 176.7521 | 2.4
5. Testing and Evaluation (Begin Date NLT 160 days from contract implementation date) |  |  |  | 2019-06-14
a. Test plan for functional, integration, system, regression and user acceptance testing |  |  |  | 2019-01-17
a. Test plan for functional, integration, system, regression and user acceptance testing | Business Lead | 154.5935 | 152.19
a. Test plan for functional, integration, system, regression and user acceptance testing | Integration Lead | 142.7341 | 54.08
a. Test plan for functional, integration, system, regression and user acceptance testing | Interface Lead | 136.8044 | 67.6
a. Test plan for functional, integration, system, regression and user acceptance testing | Senior Developer | 132.0633 | 196.04
a. Test plan for functional, integration, system, regression and user acceptance testing | Conversion Lead | 136.8044 | 67.6
a. Test plan for functional, integration, system, regression and user acceptance testing | Developer | 119.1926 | 330.4
a. Test plan for functional, integration, system, regression and user acceptance testing | Arizona Lead | 130.8746 | 201.66
a. Test plan for functional, integration, system, regression and user acceptance testing | BA | 83.4369 | 451.2
a. Test plan for functional, integration, system, regression and user acceptance testing | Senior BA | 113.0855 | 451.2
a. Test plan for functional, integration, system, regression and user acceptance testing | Hawaii Lead | 130.8746 | 201.66
a. Test plan for functional, integration, system, regression and user acceptance testing | Solution Architect | 192.5438 | 50.2
a. Test plan for functional, integration, system, regression and user acceptance testing | Server Engineer | 166.4435 | 19.6
a. Test plan for functional, integration, system, regression and user acceptance testing | Senior Integration Engineer | 195.0565 | 6.1
a. Test plan for functional, integration, system, regression and user acceptance testing | DBA | 174.878 | 10.16
a. Test plan for functional, integration, system, regression and user acceptance testing | Application Systems Admin | 176.7521 | 13.68
a. Test plan for functional, integration, system, regression and user acceptance testing | Security Lead | 154.5935 | 16.2
b. Validation of test reporting |  |  |  | 2019-06-14
b. Validation of test reporting | Business Lead | 154.5935 | 355.11
b. Validation of test reporting | Integration Lead | 142.7341 | 216.32
b. Validation of test reporting | Interface Lead | 136.8044 | 270.4
b. Validation of test reporting | Senior Developer | 132.0633 | 784.16
b. Validation of test reporting | Conversion Lead | 136.8044 | 270.4
b. Validation of test reporting | Developer | 119.1926 | 1321.6
b. Validation of test reporting | Arizona Lead | 130.8746 | 470.54
b. Validation of test reporting | BA | 83.4369 | 1052.8
b. Validation of test reporting | Senior BA | 113.0855 | 1052.8
b. Validation of test reporting | Hawaii Lead | 130.8746 | 470.54
b. Validation of test reporting | Solution Architect | 192.5438 | 200.8
b. Validation of test reporting | Server Engineer | 166.4435 | 78.4
b. Validation of test reporting | Senior Integration Engineer | 195.0565 | 24.4
b. Validation of test reporting | DBA | 174.878 | 40.64
b. Validation of test reporting | Application Systems Admin | 176.7521 | 54.72
b. Validation of test reporting | Security Lead | 154.5935 | 64.8
c. Error reporting and remediation planning for test stages |  |  |  | 2019-06-14
6. Implementation (Deliverable 10 days from Integrated Testing Acceptance) |  |  |  | 2019-07-01
a. Implementation/Roll out plan to include dashboard reporting. |  |  |  | 2019-05-29
a. Implementation/Roll out plan to include dashboard reporting. | Business Lead | 154.5935 | 24
a. Implementation/Roll out plan to include dashboard reporting. | Integration Lead | 142.7341 | 48
a. Implementation/Roll out plan to include dashboard reporting. | Interface Lead | 136.8044 | 60
a. Implementation/Roll out plan to include dashboard reporting. | Senior Developer | 132.0633 | 174
a. Implementation/Roll out plan to include dashboard reporting. | Conversion Lead | 136.8044 | 60
a. Implementation/Roll out plan to include dashboard reporting. | Developer | 119.1926 | 280
a. Implementation/Roll out plan to include dashboard reporting. | Arizona Lead | 130.8746 | 54
a. Implementation/Roll out plan to include dashboard reporting. | BA | 83.4369 | 120
a. Implementation/Roll out plan to include dashboard reporting. | Senior BA | 113.0855 | 120
a. Implementation/Roll out plan to include dashboard reporting. | Hawaii Lead | 130.8746 | 54
a. Implementation/Roll out plan to include dashboard reporting. | Solution Architect | 192.5438 | 30
a. Implementation/Roll out plan to include dashboard reporting. | Server Engineer | 166.4435 | 39.2
a. Implementation/Roll out plan to include dashboard reporting. | BC/DR Analyst | 132.9077 | 8
a. Implementation/Roll out plan to include dashboard reporting. | Senior Integration Engineer | 195.0565 | 12.2
a. Implementation/Roll out plan to include dashboard reporting. | DBA | 174.878 | 20.32
a. Implementation/Roll out plan to include dashboard reporting. | Application Systems Admin | 176.7521 | 27.36
a. Implementation/Roll out plan to include dashboard reporting. | Security Lead | 154.5935 | 10.8
a. Implementation/Roll out plan to include dashboard reporting. | Configuration Manager | 176.7521 | 9.6
b. Validated of production reports |  |  |  | 2019-06-07
b. Validated of production reports | Business Lead | 154.5935 | 12
b. Validated of production reports | Integration Lead | 142.7341 | 24
b. Validated of production reports | Interface Lead | 136.8044 | 30
b. Validated of production reports | Senior Developer | 132.0633 | 87
b. Validated of production reports | Conversion Lead | 136.8044 | 30
b. Validated of production reports | Developer | 119.1926 | 140
b. Validated of production reports | Arizona Lead | 130.8746 | 27
b. Validated of production reports | BA | 83.4369 | 60
b. Validated of production reports | Senior BA | 113.0855 | 60
b. Validated of production reports | Hawaii Lead | 130.8746 | 27
b. Validated of production reports | Solution Architect | 192.5438 | 15
b. Validated of production reports | Server Engineer | 166.4435 | 19.6
b. Validated of production reports | BC/DR Analyst | 132.9077 | 4
b. Validated of production reports | Senior Integration Engineer | 195.0565 | 6.1
b. Validated of production reports | DBA | 174.878 | 10.16
b. Validated of production reports | Application Systems Admin | 176.7521 | 13.68
b. Validated of production reports | Security Lead | 154.5935 | 5.4
b. Validated of production reports | Configuration Manager | 176.7521 | 4.8
c. Ongoing error reporting |  |  |  | 2019-06-12
c. Ongoing error reporting | Business Lead | 154.5935 | 12
c. Ongoing error reporting | Integration Lead | 142.7341 | 24
c. Ongoing error reporting | Interface Lead | 136.8044 | 30
c. Ongoing error reporting | Senior Developer | 132.0633 | 87
c. Ongoing error reporting | Conversion Lead | 136.8044 | 30
c. Ongoing error reporting | Developer | 119.1926 | 140
c. Ongoing error reporting | Arizona Lead | 130.8746 | 27
c. Ongoing error reporting | BA | 83.4369 | 60
c. Ongoing error reporting | Senior BA | 113.0855 | 60
c. Ongoing error reporting | Hawaii Lead | 130.8746 | 27
c. Ongoing error reporting | Solution Architect | 192.5438 | 15
c. Ongoing error reporting | Server Engineer | 166.4435 | 19.6
c. Ongoing error reporting | BC/DR Analyst | 132.9077 | 4
c. Ongoing error reporting | Senior Integration Engineer | 195.0565 | 6.1
c. Ongoing error reporting | DBA | 174.878 | 10.16
c. Ongoing error reporting | Application Systems Admin | 176.7521 | 13.68
c. Ongoing error reporting | Security Lead | 154.5935 | 5.4
c. Ongoing error reporting | Configuration Manager | 176.7521 | 4.8
d. SLA agreements |  |  |  | 2019-06-14
d. SLA agreements | Business Lead | 154.5935 | 6
d. SLA agreements | Integration Lead | 142.7341 | 12
d. SLA agreements | Interface Lead | 136.8044 | 15
d. SLA agreements | Senior Developer | 132.0633 | 43.5
d. SLA agreements | Conversion Lead | 136.8044 | 15
d. SLA agreements | Developer | 119.1926 | 70
d. SLA agreements | Arizona Lead | 130.8746 | 13.5
d. SLA agreements | BA | 83.4369 | 30
d. SLA agreements | Senior BA | 113.0855 | 30
d. SLA agreements | Hawaii Lead | 130.8746 | 13.5
d. SLA agreements | Solution Architect | 192.5438 | 7.5
d. SLA agreements | Server Engineer | 166.4435 | 9.8
d. SLA agreements | BC/DR Analyst | 132.9077 | 2
d. SLA agreements | Senior Integration Engineer | 195.0565 | 3.05
d. SLA agreements | DBA | 174.878 | 5.08
d. SLA agreements | Application Systems Admin | 176.7521 | 6.84
d. SLA agreements | Security Lead | 154.5935 | 2.7
d. SLA agreements | Configuration Manager | 176.7521 | 2.4
7. Post Implementation (Deliverable 60 days from Integrated Testing Acceptance) |  |  |  | 2019-08-30
a. Post implementation plan for both AHCCCS/Med-Quest |  |  |  | 2019-07-03
a. Post implementation plan for both AHCCCS/Med-Quest | Business Lead | 154.5935 | 60.75
a. Post implementation plan for both AHCCCS/Med-Quest | Integration Lead | 142.7341 | 40.5
a. Post implementation plan for both AHCCCS/Med-Quest | Interface Lead | 136.8044 | 81
a. Post implementation plan for both AHCCCS/Med-Quest | Senior Developer | 132.0633 | 222.75
a. Post implementation plan for both AHCCCS/Med-Quest | Conversion Lead | 136.8044 | 81
a. Post implementation plan for both AHCCCS/Med-Quest | Developer | 119.1926 | 374
a. Post implementation plan for both AHCCCS/Med-Quest | Arizona Lead | 130.8746 | 72.9
a. Post implementation plan for both AHCCCS/Med-Quest | BA | 83.4369 | 162
a. Post implementation plan for both AHCCCS/Med-Quest | Senior BA | 113.0855 | 162
a. Post implementation plan for both AHCCCS/Med-Quest | Hawaii Lead | 130.8746 | 72.9
a. Post implementation plan for both AHCCCS/Med-Quest | Solution Architect | 192.5438 | 40.5
b. Post implementation documentation delivery |  |  |  | 2019-08-16
b. Post implementation documentation delivery | Business Lead | 154.5935 | 36.45
b. Post implementation documentation delivery | Integration Lead | 142.7341 | 24.3
b. Post implementation documentation delivery | Interface Lead | 136.8044 | 48.6
b. Post implementation documentation delivery | Senior Developer | 132.0633 | 133.65
b. Post implementation documentation delivery | Conversion Lead | 136.8044 | 48.6
b. Post implementation documentation delivery | Developer | 119.1926 | 224.4
b. Post implementation documentation delivery | Arizona Lead | 130.8746 | 43.74
b. Post implementation documentation delivery | BA | 83.4369 | 97.2
b. Post implementation documentation delivery | Senior BA | 113.0855 | 97.2
b. Post implementation documentation delivery | Hawaii Lead | 130.8746 | 43.74
b. Post implementation documentation delivery | Solution Architect | 192.5438 | 24.3
c. Post implementation support/maintenance plan |  |  |  | 2019-08-19
c. Post implementation support/maintenance plan | Business Lead | 154.5935 | 72.9
c. Post implementation support/maintenance plan | Integration Lead | 142.7341 | 48.6
c. Post implementation support/maintenance plan | Interface Lead | 136.8044 | 97.2
c. Post implementation support/maintenance plan | Senior Developer | 132.0633 | 267.3
c. Post implementation support/maintenance plan | Conversion Lead | 136.8044 | 97.2
c. Post implementation support/maintenance plan | Developer | 119.1926 | 448.8
c. Post implementation support/maintenance plan | Arizona Lead | 130.8746 | 87.48
c. Post implementation support/maintenance plan | BA | 83.4369 | 194.4
c. Post implementation support/maintenance plan | Senior BA | 113.0855 | 194.4
c. Post implementation support/maintenance plan | Hawaii Lead | 130.8746 | 87.48
c. Post implementation support/maintenance plan | Solution Architect | 192.5438 | 48.6
d. Error reporting and remediation planning |  |  |  | 2019-08-15
d. Error reporting and remediation planning | Business Lead | 154.5935 | 72.9
d. Error reporting and remediation planning | Integration Lead | 142.7341 | 48.6
d. Error reporting and remediation planning | Interface Lead | 136.8044 | 97.2
d. Error reporting and remediation planning | Senior Developer | 132.0633 | 267.3
d. Error reporting and remediation planning | Conversion Lead | 136.8044 | 97.2
d. Error reporting and remediation planning | Developer | 119.1926 | 448.8
d. Error reporting and remediation planning | Arizona Lead | 130.8746 | 87.48
d. Error reporting and remediation planning | BA | 83.4369 | 194.4
d. Error reporting and remediation planning | Senior BA | 113.0855 | 194.4
d. Error reporting and remediation planning | Hawaii Lead | 130.8746 | 87.48
d. Error reporting and remediation planning | Solution Architect | 192.5438 | 48.6
8. IV&V Coordination and Reporting (This is an ongoing requirement from date of contraction implementation through System Certification by CMS. Targeted end date is December 2019) |  |  |  | Ongoing thru 12/31/2019
a. Timely response to all request from IV&V |  |  |  | Ongoing thru 12/31/2019
a. Timely response to all request from IV&V | Project Manager | 172.3827 | 373.92
a. Timely response to all request from IV&V | Business Lead | 154.5935 | 233.52
a. Timely response to all request from IV&V | Integration Lead | 142.7341 | 373.92
a. Timely response to all request from IV&V | Senior Developer | 132.0633 | 233.52
b. Quarterly reporting |  |  |  | Ongoing thru 12/31/2019
b. Quarterly reporting | Project Manager | 172.3827 | 124.64
b. Quarterly reporting | Business Lead | 154.5935 | 77.84
b. Quarterly reporting | Integration Lead | 142.7341 | 124.64
b. Quarterly reporting | Senior Developer | 132.0633 | 77.84
c. Milestone reporting |  |  |  | Ongoing thru 12/31/2019
c. Milestone reporting | Project Manager | 172.3827 | 124.64
c. Milestone reporting | Business Lead | 154.5935 | 77.84
c. Milestone reporting | Integration Lead | 142.7341 | 124.64
c. Milestone reporting | Senior Developer | 132.0633 | 77.84
Totals |  | 5515578.9616 | 41985