## Summary
SOLICITATION # YH19-0025
ELECTRONIC VISIT VERIFICATION SYSTEM
BAFO ATTACHMENT B: PRICING PROPOSAL WORKSHEET
OFFEROR NAME: |  |  | Sandata Technologies, LLC
Total System Cost Summaries
This will be the Total Cost Summaries from each of the Tabs in this spreadsheet
Description | Year 1 Costs | Year 2 Costs | Year 3 Costs | Year 4 Costs | Year 5 Costs
Implementation Costs | 547520
Data Collection Costs | 823166.25 | 1699569.375 | 1752466.125 | 1812475.125 | 1877774.25
Devices | 5037860.2083 | 5495847.5 | 5495847.5 | 4281017.36 | 4281017.36
Data Aggregation Costs | 625287.1875 | 1291013.625 | 1331194.5 | 1376778 | 1426380
Yearly Totals | 1995973.4375 | 2990583 | 3083660.625 | 3189253.125 | 3304154.25
5-year Cost of Ownership:
14563624.4375

## DC Operation
RFP - YH19-0025
ELECTRONIC VISIT VERIFICATION SYSTEM
DATA COLLECTION OPERATIONAL COSTS
Provide a line item for all recommended cost based on the proposed solution
Description | Year 1 - Per Transaction Maintenance Cost | Year 2 - Per Transaction Maintenance Cost | Year 3 - Per Transaction Maintenance Cost | Year 4 - Per Transaction Maintenance Cost | Year 5 - Per Transaction Maintenance Cost
HARDWARE
Server Hardware (if applicable):
A) Number of cores | 0 | 0 | 0 | 0 | 0
B) Disk Space | 0 | 0 | 0 | 0 | 0
SOFTWARE
Subscription Pricing (if applicable) | 0 | 0 | 0 | 0 | 0
Server Software (if applicable) | 0 | 0 | 0 | 0 | 0
Database Software (if applicable) | 0 | 0 | 0 | 0 | 0
License Fees (if applicable) | 0 | 0 | 0 | 0 | 0
Transaction Fees (if applicable) | 1646332.5 | 1699569.375 | 1752466.125 | 1812475.125 | 1877774.25
Hosting Fees (if applicable) | 0 | 0 | 0 | 0 | 0
OPERATIONAL LABOR
Staffing |  | 0 | 0 | 0 | 0
Standard Assumptions | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Visit Transaction Count | 4390220 | 4532185 | 4673243 | 4833267 | 5007398
Total Cost | 1646332.5 | 1699569.375 | 1752466.125 | 1812475.125 | 1877774.25
Total Per Transaction Maintenance Cost: | 0.375 | 0.375 | 0.375 | 0.375 | 0.375
AHCCCS snd Med-QUEST Assumptions
The visit transaction count was derived from claim lines and on average there are 2.5 visits/claim lines per claim.
Claims estimates assume 56.8% of claims from providers that will use the AHCCCS/Med-Quest EVV Vendor system
Claim estimates contemplate a FFY 20 – FFY 24 claim projections forecast of enrollment growth in the affected programs for both AHCCCS and Med-QUEST.
Device costs shall be listed on spreadsheet named "Devices" and included in the Summary Spreadsheet.

## DA Operation
RFP - YH19-0025
ELECTRONIC VISIT VERIFICATION SYSTEM
DATA AGGREGATION OPERATIONAL COSTS
Provide a line item for all recommended cost based on the proposed solution
Description | Year 1 - Per Transaction Maintenance Cost | Year 2 - Per Transaction Maintenance Cost | Year 3 - Per Transaction Maintenance Cost | Year 4 - Per Transaction Maintenance Cost | Year 5 - Per Transaction Maintenance Cost
HARDWARE
Server Hardware (if applicable):
A) Number of cores | 0 | 0 | 0 | 0 | 0
B) Disk Space | 0 | 0 | 0 | 0 | 0
C) List other components | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
SOFTWARE
Subscription Pricing (if applicable) | 0 | 0 | 0 | 0 | 0
Server Software (if applicable) | 0 | 0 | 0 | 0 | 0
Database Software (if applicable) | 0 | 0 | 0 | 0 | 0
License Fees (if applicable) | 0 | 0 | 0 | 0 | 0
Transaction Fees (if applicable) | 1250574.375 | 1291013.625 | 1331194.5 | 1376778 | 1426380
Hosting Fees (if applicable) | 0 | 0 | 0 | 0 | 0
OPERATIONAL LABOR
Staffing | 0 | 0 | 0 | 0 | 0
Standard Assumptions | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Visit Transaction Count | 3334865 | 3442703 | 3549852 | 3671408 | 3803680
Total Cost | 1250574.375 | 1291013.625 | 1331194.5 | 1376778 | 1426380
Total Per Transaction Maintenance Cost: | 0.375 | 0.375 | 0.375 | 0.375 | 0.375
AHCCCS and Med-QUEST Assumptions
The visit transaction count was derived from claim lines and on average there are 2.5 visits/claim lines per claim.
Claims estimates assume 43.2% of claims from providers that already have an EVV system
Claim estimates contemplate a FFY 20 – FFY 24 claim projections forecast of enrollment growth in the affected programs for both AHCCCS and Med-QUEST.

## Implementation
SOLICITATION # YH19-0025
ELECTRONIC VISIT VERIFICATION SOLUTION
IMPLEMENTATION PRICING
Implementation is the time from contract execution through the CMS Certification Milestone as described in the MECL (https://www.medicaid.gov/medicaid/data-and-systems/mect/index.html)
Provide a line item for all implementation costs.
Description | (June) Q4 SFY 2019 | Q1 SFY 2020 | Q2 SFY 2020 | Q3 SFY 2020 | Q4 SFY 2020 | Q1 SFY 2021 | Total
Project Management | 10395 | 31500 | 21105 | 0 | 0 | 0 | 63000
Configuration | 15300 | 45900 | 0 | 0 | 0 | 0 | 61200
Interfaces | 0 | 0 | 0 | 0 | 0 | 0 | 0
Data Conversion | 0 | 0 | 0 | 0 | 0 | 0 | 0
Testing | 0 | 32400 | 0 | 0 | 0 | 0 | 32400
Training | 0 | 73368 | 110052 | 0 | 0 | 0 | 183420
Deployment/Installation | 0 | 32400 | 8100 | 0 | 0 | 0 | 40500
Post Implementation Support | 0 | 0 | 25560 | 69300 | 22140 | 0 | 117000
Documentation | 0 | 0 | 0 | 0 | 0 | 0 | 0
Travel | 10000 | 25000 | 15000 | 0 | 0 | 0 | 50000
Other | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Cost: | 35695 | 240568 | 179817 | 69300 | 22140 | 0 | 547520
Offeror's Assumptions shall be listed on a separate sheet.
Implementation Costs shall all travel. Use the Section 7.1 of the Scope of Work for estimating travel:
*For Requirements Section of the Scope of Work: 1-2 trips for each State
*For Development: No travel should be assumed
*For Testing the System: 1 trip should be assumed for each State
*For Implementation of the System: 1-2 trips should be assumed for each State
*For Training: 1-2 trips should be assumed for each State
*The duration should be assumed to be 2-3 days per trip for each State

## Implementation Deliverables
SOLICITATION # YH19-0025
ELECTRONIC VISIT VERIFICATION SYSTEM
IMPLEMENTATION DELIVERABLES
The primary project deliverable for Implementation will be a completed Electronic Visit Verification System that includes the following. Please complete all columns of this attachment and submit with response.
Deliverable | Staff Titles | Hourly Rate | # of Hours | Proposed Timeline
1. Project Management (Weekly and on-going as defined) | Implementation Director | 150 | 700 | Continuous- June 2019 through December 2019
a. Weekly IT Planning Session involvement | Implementation Director | 150 | 24 | Continuous- June 2019 through December 2019
b. Develop milestone schedule. (weekly, monthly and quarterly) | Implementation Director | 150 | 48 | Continuous- June 2019 through December 2019
c. Contributions to the overall project plan maintained by AHCCCS/Med-QUEST | Implementation Director | 150 | 48 | Continuous- June 2019 through December 2019
2. Business process analysis and system requirements document (Deliverable within 30 days from contract implementation) | Solution Architect | 150 | 376 | June - mid-July 2019: 90% (business rules) mid-July - mid-Aug 2019: 50% (interfaces) mid-Aug - December 2019: 10% (ongoing support)
a. Baseline Review (includes Project Start-Up along with Administrative and Baseline Reviews) | Solution Architect | 150 | 60 | June - July 2019: 75% (business rules) mid-July - December 2019: 10% (ongoing support)
b. System Security Assessment | Solution Architect | 150 | 20 | Aug - mid-Aug 2019: 25%
c. Data/System Security Plan | Solution Architect | 150 | 20 | Aug - mid-Aug 2019: 25%
d. Data Use/Exchange Interconnection Security Agreement | Solution Architect | 150 | 20 | Aug - mid-Aug 2019: 25%
e. Risk Assessment Plan | Solution Architect | 150 | 20 | Aug - mid-Aug 2019: 25%
f. Complete Privacy Impact Analysis (PIA) | Solution Architect | 150 | 20 | Aug - mid-Aug 2019: 25%
3. System Design (Deliverable 60-90 days from contract implementation agreed upon between AHCCCS/Med-QUEST and Contractor) | Solution Architect | 150 | 304 | June - July 2019: 50% (preparations) July - Sept 2019: 90% (system design / config)
a. Interface Design/Control document. COTS to mainframe interface design. | Technical Design | 150 | 180 | July - late-July 2019: 90% late-July - Sept 2019: 25%
b. Architecture walkthrough and requirements analysis | Implementation Director, Solution Architect | 150 | 16 | 2019-06-01
c. Database design | Technical Design | 150 | 0 | n/a
d. Detailed Design Review (includes Preliminary and Detailed Design Reviews) | Technical Design | 150 | 10 | Late June 2019
e. Final Detailed Design Review | Technical Design | 150 | 2 | Late June 2019
f. Data conversion analysis and conversion plan | Technical Design | 150 | 96 | July - Sept 2019
4. Development (Begin date NLT 120 days from contract implementation date) | Technical Design | 150 | 360 | July - Sept 2019
a. Portals, for user access | Technical Design | 150 | 144 | July - Sept 2019
b. User training plan (knowledge transfer, desktop manuals, on-site training) | Training Team | 150 | 180 | mid-Aug - mid-Sept 2019
c. Contingency Plan/Recovery Plan | Technical Design | 150 | 20 | Aug - mid-Aug 2019
d. Reporting module and report develoment | Technical Design | 150 | 16 | 2019-09-01
5. Testing and Evaluation (Begin Date NLT 160 days from contract implementation date) | UAT Director | 150 | 360 | mid-July - mid-Sept 2019
a. Test plan for functional, integration, system, regression and user acceptance testing | UAT Director | 150 | 90 | early Aug 2019
b. Validation of test reporting | UAT Director | 150 | 30 | mid-Sept 2019
c. Error reporting and remediation planning for test stages | UAT Director | 150 | 30 | mid-Sept 2019
6. Implementation (Deliverable 10 days from Integrated Testing Acceptance) | Implementation Director | 150 | 90 | late-Sept - October 2019
a. Implementation/Roll out plan to include dashboard reporting. | Implementation Director | 150 | 20 | late-Sept - October 2019
b. Validated of production reports | Implementation Director | 150 | 10 | late-Sept - October 2019
c. Ongoing error reporting | Implementation Director | 150 | 10 | late-Sept - October 2019
d. SLA agreements | Implementation Director | 150 | 10 | late-Sept - October 2019
7. Post Implementation (Deliverable 60 days from Integrated Testing Acceptance) | Implementation Director / Account Manager | 150 | 480 | December - February 2019
a. Post implementation plan for both AHCCCS/Med-Quest | Implementation Director / Account Manager | 150 | 40 | late Nov - December 2019
b. Post implementation documentation delivery | Implementation Director / Account Manager | 150 | 30 | December 2019 - February 2020
c. Post implementation support/maintenance plan | Implementation Director / Account Manager | 150 | 40 | December 2019 - February 2020
d. Error reporting and remediation planning | Implementation Director / Account Manager | 150 | 80 | December 2019 - February 2020
8. IV&V Coordination and Reporting (This is an ongoing requirement from date of contraction implementation through System Certification by CMS. Targeted end date is December 2019) | CMS / MITA Expert | 150 | 820 | June 2019 - July 2020
a. Timely response to all request from IV&V | CMS / MITA Expert | 150 | 224 | June 2019 - July 2020
b. Quarterly reporting | CMS / MITA Expert | 150 | 48 | September 2019 / December 2019 / March 2020 / June 2020
c. Milestone reporting | CMS / MITA Expert | 150 | 224 | Weekly, June 2019 - July 2020
Note on A30: Johnson, Dara: This looks like it needs to be revised to reflect the EVV System. Should it simply say "user access portals?"
Note on A33: Johnson, Dara: We felt it was important to add the development of the reporting modules and the reports themselves into this list.

## Devices
EVV DEVICE PRICING
Pricing Model & Instructions
1. The State will pay a fixed monthly price per device, applicable to all devices in active use in a given month.
2. Price is all-inclusive, including:
a. Device costs - initial device, and repair/maintenance and replacement in all circumstances (e.g. damage, loss, and theft).
b. Shipping costs - all shipping and handling services for all devices, including replacements.
c. Data Service costs - wireless carrier monthly data service charges.
d. Support costs - customer service and technical assistance for users.
3. Contractor populates C28:F28 higlighted in blue with % of device distribution based upon experience.
a. The user column should include any and all DCW and member owned devices that are electively used for EVV.
(i.e. DCW mobile phone, member land line for telephony, etc.).
b. The state has provided an assumption of 55,000 total number of devices (C:25) based upon the member population,
population of DCWs and assumed ratios of of the number of DCWs to members.
4. Contractor populates C32:F35 highlighted in yellow with cost components for each device type.
5. Contractor will be responsible for all costs required in order to ensure a working device is provided.
a. Contractor should make relevant assumptions regarding device "churn" rate due to damage, loss, and theft.
b. Contractor is "at risk" for any increase in pricing of cost components, as well as repair/replacement.
6. Contracted fixed price is the monthly fee for each device calculated in C39:F39, highlighted in green.
Assumptions
| Devices by Type | User | Fob | Bluetooth | Mobile Phone | Total | Member Classifications | Total Population | 1:1 (Member to DCW Ratio)* | 2:1 (DCWs to Members)
| % Distribution (Est.) | 35% | 10% |  | 55% | 100% | AZ Acute | 38515 |  | 38515
| Devices by Option (Est.) | 19250 | 5500 | 0 | 30250 | 55000 | AZ LTSS | 47269 | 18907 | 28362
[7 empty] | HI Acute | 3300 |  | 3300
| Cost Components (Annual) | User | Fob | Bluetooth | Mobile Phone |  | HI LTSS | 2178 |  | 2178
| Device | 0 | 50 | 0 | 60.65 |  | Total | 91262 | 18907 | 72355
| Shipping | 0 | 0 | 0 | 11.97
| Data Service | 0 | 0 | 0 | 80.22 |  | DCW Population Total |  | 18907 | 36177.5 | 55084.5
| Support | 0 | 0 | 0 | 19.75
| Total Annual Cost | 0 | 50 | 0 | 172.59 |  | *Based upon the Prop 206 report, we know that 40% of members
are served by family members.
| Price per Device (All-Inclusive) | User | Fob | Bluetooth | Mobile Phone | Total | This number is consistent with the number of active DCWs
| Monthly Fee (Fixed) | 0 | 4.1667 | 0 | 14.3825 |  | we have in our online database.
| Total Monthly Fee (Est.) | 0 | 22916.6667 | 0 | 435070.625 | 457987.2917
| Total Annual Fee (Est.) | 0 | 275000 | 0 | 5220847.5 | 5495847.5
Estimate yearly fees based upon projected number of devices required.
| Description | Year 1 Costs | Year 2 Costs | Year 3 Costs | Year 4 Costs | Year 5 Costs
Devices
| Yearly Totals | 5037860.2083 | 5495847.5 | 5495847.5 | 4281017.36 | 4281017.36
Note on I26: Johnson, Dara: Delete this.