## Summary
SOLICITATION # YH19-0025
ELECTRONIC VISIT VERIFICATION SYSTEM
ATTACHMENT B: PRICING PROPOSAL WORKSHEET
OFFEROR NAME: |  |  | Sandata Technologies, LLC
Total System Cost Summaries
This will be the Total Cost Summaries from each of the Tabs in this spreadsheet
Description | Year 1 Costs | Year 2 Costs | Year 3 Costs | Year 4 Costs | Year 5 Costs
Implementation Costs | 758420 | 0 | 0 | 0 | 0
Data Collection Costs | 1229382.61 | 2538265.63 | 2617257.88 | 2706871.32 | 2804384.76
Data Aggregation Costs | 650298.605 | 1342654.17 | 1384442.3 | 1431849.21 | 1483435.34
Yearly Totals | 2638101.215 | 3880919.8 | 4001700.18 | 4138720.53 | 4287820.1
*The above costs do not include devices which are priced separately in the pricing assumptions.
5-year Cost of Ownership:
18947261.825

## DC Operation
RFP - YH19-0025
ELECTRONIC VISIT VERIFICATION SYSTEM
DATA COLLECTION OPERATIONAL COSTS
Provide a line item for all recommended cost based on the proposed solution
Description | Year 1 - Per Transaction Maintenance Cost | Year 2 - Per Transaction Maintenance Cost | Year 3 - Per Transaction Maintenance Cost | Year 4 - Per Transaction Maintenance Cost | Year 5 - Per Transaction Maintenance Cost
HARDWARE
Server Hardware (if applicable):
A) Number of cores | 0 | 0 | 0 | 0 | 0
B) Disk Space | 0 | 0 | 0 | 0 | 0
C) List other components | 0 | 0 | 0 | 0 | 0
Devices (list all types) | 129.97 | 129.97 | 129.97 | 129.97 | 129.97
Device Installation as applicable | 0 | 0 | 0 | 0 | 0
Device Replacement Costs | 0 | 0 | 0 | 0 | 0
Replacement Costs/Maintentance/Support | 0 | 0 | 0 | 0 | 0
Device Shipping / Delivery | 11.97 | 11.97 | 11.97 | 11.97 | 11.97
Device Maintenance/Support | 99.97 | 99.97 | 99.97 | 99.97 | 99.97
SOFTWARE
Subscription Pricing (if applicable) | 0 | 0 | 0 | 0 | 0
Server Software (if applicable) | 0 | 0 | 0 | 0 | 0
Database Software (if applicable) | 0 | 0 | 0 | 0 | 0
License Fees (if applicable) | 0 | 0 | 0 | 0 | 0
Transaction Fees (if applicable) | 2458523.31 | 2538023.72 | 2617015.97 | 2706629.41 | 2804142.85
Hosting Fees (if applicable) |  | 0 | 0 | 0 | 0
OPERATIONAL LABOR
Staffing | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
Standard Assumptions | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Visit Transaction Count | 4390220.1915 | 4532185.2182 | 4673242.7984 | 4833266.7957 | 5007397.9467
Total Cost | 2458765.22 | 2538265.63 | 2617257.88 | 2706871.32 | 2804384.76
Total Per Transaction Maintenance Cost: | 0.56006 | 0.56005 | 0.56005 | 0.56005 | 0.56005
AHCCCS snd Med-QUEST Assumptions
Claims estimates assume 56.8% of claims from providers that will use the AHCCCS/Med-Quest EVV Vendor system
Claim estimates contemplate a FFY 20 – FFY 24 claim projections forecast of enrollment growth in the affected programs for both AHCCCS and Med-QUEST.
Offeror's Assumptions shall be listed on a separate sheet.

## DA Operation
RFP - YH19-0025
ELECTRONIC VISIT VERIFICATION SYSTEM
DATA AGGREGATION OPERATIONAL COSTS
Provide a line item for all recommended cost based on the proposed solution
Description | Year 1 - Per Transaction Maintenance Cost | Year 2 - Per Transaction Maintenance Cost | Year 3 - Per Transaction Maintenance Cost | Year 4 - Per Transaction Maintenance Cost | Year 5 - Per Transaction Maintenance Cost
HARDWARE
Server Hardware (if applicable):
A) Number of cores | 0 | 0 | 0 | 0 | 0
B) Disk Space | 0 | 0 | 0 | 0 | 0
C) List other components | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
SOFTWARE
Subscription Pricing (if applicable) | 0 | 0 | 0 | 0 | 0
Server Software (if applicable) | 0 | 0 | 0 | 0 | 0
Database Software (if applicable) | 0 | 0 | 0 | 0 | 0
License Fees (if applicable) | 0 | 0 | 0 | 0 | 0
Transaction Fees (if applicable) | 1300597.21 | 1342654.17 | 1384442.3 | 1431849.21 | 1483435.34
Hosting Fees (if applicable) |  | 0 | 0 | 0 | 0
OPERATIONAL LABOR
Staffing | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
Standard Assumptions | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Visit Transaction Count | 3334864.6516 | 3442703.0125 | 3549852.0659 | 3671408.2405 | 3803680.3806
Total Cost | 1300597.21 | 1342654.17 | 1384442.3 | 1431849.21 | 1483435.34
Total Per Transaction Maintenance Cost: | 0.39 | 0.39 | 0.39 | 0.39 | 0.39
AHCCCS and Med-QUEST Assumptions
Claims estimates assume 43.2% of claims from providers that already have an EVV system
Claim estimates contemplate a FFY 20 – FFY 24 claim projections forecast of enrollment growth in the affected programs for both AHCCCS and Med-QUEST.
Offeror's Assumptions shall be listed on a separate sheet.

## Implementation
SOLICITATION # YH19-0025
ELECTRONIC VISIT VERIFICATION SOLUTION
IMPLEMENTATION PRICING
Implementation is the time from contract execution through the CMS Certification Milestone as described in the MECL (https://www.medicaid.gov/medicaid/data-and-systems/mect/index.html)
Provide a line item for all implementation costs.
Description | Q1 SFY 2019 | Q2 SFY 2019 | Q3 SFY 2019 | Q4 SFY 2019 | Q1 SFY 2020 | Q2 SFY 2020 | Total
Project Management | 0 | 26250 | 26250 | 26250 | 26250 | 0 | 105000
Configuration | 0 | 65100 | 36900 | 0 | 0 | 0 | 102000
Interfaces | 0 | 0 | 0 | 0 | 0 | 0 | 0
Data Conversion | 0 | 0 | 0 | 0 | 0 | 0 | 0
Testing | 0 | 10800 | 43200 | 0 | 0 | 0 | 54000
Training | 0 | 0 | 137565 | 45855 | 0 | 0 | 183420
Deployment/Installation | 0 | 54000 | 15000 | 0 | 0 | 0 | 69000
Post Implementation Support | 0 | 0 | 0 | 97500 | 97500 | 0 | 195000
Documentation | 0 | 0 | 0 | 0 | 0 | 0 | 0
Travel | 0 | 10000 | 25000 | 15000 | 0 | 0 | 50000
Other | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Cost: | 0 | 166150 | 283915 | 184605 | 123750 | 0 | 758420
Offeror's Assumptions shall be listed on a separate sheet.
Implementation Costs shall all travel. Use the Section 7.1 of the Scope of Work for estimating travel:
*For Requirements Section of the Scope of Work: 1-2 trips for each State
*For Development: No travel should be assumed
*For Testing the System: 1 trip should be assumed for each State
*For Implementation of the System: 1-2 trips should be assumed for each State
*For Training: 1-2 trips should be assumed for each State
*The duration should be assumed to be 2-3 days per trip for each State

## Implementation Deliverables
SOLICITATION # YH19-0025
ELECTRONIC VISIT VERIFICATION SYSTEM
IMPLEMENTATION DELIVERABLES
The primary project deliverable for Implementation will be a completed Electronic Visit Verification System that includes the following. Please complete all columns of this attachment and submit with response.
Deliverable | Staff Titles | Hourly Rate | # of Hours | Proposed Timeline
1. Project Management (Weekly and on-going as defined) | Implementation Director | 150 | 580 | Continuous- April 2019 through October 2019
a. Weekly IT Planning Session involvement | Implementation Director | 150 | 24 | Continuous- April 2019 through October 2019
b. Develop milestone schedule. (weekly, monthly and quarterly) | Implementation Director | 150 | 48 | Continuous- April 2019 through October 2019
c. Contributions to the overall project plan maintained by AHCCCS/Med-QUEST | Implementation Director | 150 | 48 | Continuous- April 2019 through October 2019
2. Business process analysis and system requirements document (Deliverable within 30 days from contract implementation) | Solution Architect | 150 | 216 | April 2019- mid-May 2019: 100% (business rules) mid-May 2019 - mid-June 2019: 50% (interfaces) mid-June 2019 - October 2019: 10% (ongoing support)
a. Baseline Review (includes Project Start-Up along with Administrative and Baseline Reviews) | Solution Architect | 150 | 60 | April 2019 - May 2019: 75% (business rules) mid-May 2019 - October 2019: 10% (ongoing support)
b. System Security Assessment | Solution Architect | 150 | 20 | June 2019 - mid-June 2019: 25%
c. Data/System Security Plan | Solution Architect | 150 | 20 | June 2019 - mid-June 2019: 25%
d. Data Use/Exchange Interconnection Security Agreement | Solution Architect | 150 | 20 | June 2019 - mid-June 2019: 25%
e. Risk Assessment Plan | Solution Architect | 150 | 20 | June 2019 - mid-June 2019: 25%
f. Complete Privacy Impact Analysis (PIA) | Solution Architect | 150 | 20 | June 2019 - mid-June 2019: 25%
3. System Design (Deliverable 60-90 days from contract implementation agreed upon between AHCCCS/Med-QUEST and Contractor) | Solution Architect | 150 | 0 | April 2019 - May 2019: 50% (preparations) May 2019 - July 2019: 100% (system design / config)
a. Interface Design/Control document. COTS to mainframe interface design. | Technical Design | 150 | 180 | May 2019 - late-May 2019: 100% late-May 2019 - July 2019: 25%
b. Architecture walkthrough and requirements analysis | Implementation Director, Solution Architect | 150 | 16 | April 19
c. Database design | Technical Design | 150 | 0 | n/a
d. Detailed Design Review (includes Preliminary and Detailed Design Reviews) | Technical Design | 150 | 10 | Late April 2019
e. Final Detailed Design Review | Technical Design | 150 | 2 | Late April 2019
f. Data conversion analysis and conversion plan | Technical Design | 150 | 96 | May 2019 - July 2019
4. Development (Begin date NLT 120 days from contract implementation date) | Technical Design | 150 | 0 | May 2019 - July 2019
a. Portals, for user access | Technical Design | 150 | 144 | May 2019 - July 2019
b. User training plan (knowledge transfer, desktop manuals, on-site training) | Training Team | 150 | 180 | mid-June 2019 - mid-July 2019
c. Contingency Plan/Recovery Plan | Technical Design | 150 | 20 | June 2019 - mid-June 2019
d. Reporting module and report develoment | Technical Design | 150 | 16 | July 19
5. Testing and Evaluation (Begin Date NLT 160 days from contract implementation date) | UAT Director | 150 | 210 | mid-May 2019 - mid-July 2019
a. Test plan for functional, integration, system, regression and user acceptance testing | UAT Director | 150 | 90 | early June 2019
b. Validation of test reporting | UAT Director | 150 | 30 | mid-July 2019
c. Error reporting and remediation planning for test stages | UAT Director | 150 | 30 | mid-July 2019
6. Implementation (Deliverable 10 days from Integrated Testing Acceptance) | Implementation Director | 150 | 50 | late-July 2019 - August 2019
a. Implementation/Roll out plan to include dashboard reporting. | Implementation Director | 150 | 20 | late-July 2019 - August 2019
b. Validated of production reports | Implementation Director | 150 | 10 | late-July 2019 - August 2019
c. Ongoing error reporting | Implementation Director | 150 | 10 | late-July 2019 - August 2019
d. SLA agreements | Implementation Director | 150 | 10 | late-July 2019 - August 2019
7. Post Implementation (Deliverable 60 days from Integrated Testing Acceptance) | Implementation Director / Account Manager | 150 | 290 | October 2019 - December 2019
a. Post implementation plan for both AHCCCS/Med-Quest | Implementation Director / Account Manager | 150 | 40 | late September 2019 - October 2019
b. Post implementation documentation delivery | Implementation Director / Account Manager | 150 | 30 | October 2019 - December 2019
c. Post implementation support/maintenance plan | Implementation Director / Account Manager | 150 | 40 | October 2019 - December 2019
d. Error reporting and remediation planning | Implementation Director / Account Manager | 150 | 80 | October 2019 - December 2019
8. IV&V Coordination and Reporting (This is an ongoing requirement from date of contraction implementation through System Certification by CMS. Targeted end date is December 2019) | CMS / MITA Expert | 150 | 324 | April 2019 - May 2020
a. Timely response to all request from IV&V | CMS / MITA Expert | 150 | 224 | April 2019 - May 2020
b. Quarterly reporting | CMS / MITA Expert | 150 | 48 | July 2019 / October 2019 / January 2020 / April 2020
c. Milestone reporting | CMS / MITA Expert | 150 | 224 | Weekly, April 2019 - May 2020
Note on A30: Johnson, Dara: This looks like it needs to be revised to reflect the EVV System. Should it simply say "user access portals?"
Note on A33: Johnson, Dara: We felt it was important to add the development of the reporting modules and the reports themselves into this list.