| MILESTONE | REIMBURSABLE COSTS | DOCUMENTATION | Timeline |
| --- | --- | --- | --- |
| Site Acquisition/ Control (if necessary) | Cost of Site Purchase and Fees Inspections and other pre-purchase assessment Reimbursement may not exceed Appraisal. | 3d Party Appraisal Purchase Contract Proof of Sale Copies of any pre-purchase inspections Approval of final project budget | Site Acquisition; 0-60. Due Diligence; 0-45. Closing; 45-60; 15. |
| Approval of Facility Plans, inspections, licenses, permits or pre-construction expenses | Cost of fees, architectural/professional design fees, permits, etc. | CER including all supporting documentation of expenses. Construction Manager approval and certification of readiness to proceed. Proof of all Construction licenses and permits. Proof of Insurance AHCCCS approved Operating Agreement executed between Owner and Operator (if separate entities). | Design; 0-180; 60. Bidding; 90-120; 30. CDs submitted for permit; 120. Permit; 180; 60. |
| Construction Milestones:  20% Completion  40% Completion  60% Completion  80% Completion  100% Complete – Cert. of Occupancy | Cost of partial construction completed – may not exceed completion milestone percentage of cost. | CER including all supporting documentation of expenses. Construction Manager site inspection, review and approval of percentage completed and compliance with budget and agreed to timeframes. Final release must include copy of Certificate of Occupancy and all final inspections and approvals (e.g. utilities, mechanical). | Start of Construction; 180; # days. Grading; 10. Underground; 15. Concrete; 15. Frame walls; 15. MFP's; 14. Windows; 5. Roofing; 5. Stucco; 14. Insulation; 3. Drywall; 24. Paving; 10. Doors; 8. Cabinets; 7. Paint; 7. Trim Out; 8. Flooring; 7. Final Clean; 3. TCO; 3. Total Construction Days; 154. |
| Licensure Approval and Occupancy | Release of Retention. | CER for final reimbursement and release of funds. Submission of all Project and sub-contractor lien waivers. Notice of ADHS approval of residential facility license(s) and applications. Documentation of move in/occupancy | Licensure 30 days post CofO |
| Change Orders/Budget Amendments | May not exceed amount held in budgeted contingency reserve. | CER for request change order expenses. Change order must have prior approval of Construction Manager and AHCCCS. |  |