## Sheet1
Days
500 W Grant Development Schedule
Item
# days
Site Acquisition | 0-60
Due Diligence, Outreach to Community Officials and Neighborhoods | 0-45
Closing | 45-60 | 15
Design | 0-180 | 60
Bidding | 90-120 | 30
CDs submitted for permit | 120
Permit | 180 | 60
Start of Construction | 180 | # days
Grading |  | 10
Underground |  | 15
Concrete |  | 15
Frame walls |  | 15
MFP's |  | 14
Windows |  | 5
Roofing |  | 5
Stucco |  | 14
Insulation |  | 3
Drywall |  | 24
Paving |  | 10
Doors |  | 8
Cabinets |  | 7
Paint |  | 7
Trim Out |  | 8
Flooring |  | 7
Final Clean |  | 3
TCO |  | 3
Total Construction Days | 154
Total Development Days | 334