Recovery Health Partners, LLC

Responses to Questions for all Proposers

The proposer needs to define whether this facility will be designed as an Article 3. Behavioral Health Inpatient Facility, pp.60-76, or as an Article 7. Behavioral Health Residential Facilities, pp.131-150 of the Arizona Administrative CODE, Title 9, Chapter 10, www.azsos.gov (copy attached).

The two proposed facilities will be designed in accordance with Article 7, Behavioral Health Residential Facilities.

Complete and resubmit the attached Cost Estimate Schedule of Values for the construction of one Facility.  Also include a detailed construction schedule which includes permits and any upfront outreach.

A Cost Estimate Schedule of Values for one of our two proposed Secure Behavioral Health Residential facilities is attached. Costs for both facilities are expected to be the same. In addition, a detailed construction schedule for the two facilities is attached.

Is the land acquisition costs based on actual land costs?

Land acquisition costs are based upon actual land costs. These costs are included in the purchase and sale agreements currently in escrow, awaiting grant award decision. These purchase contracts were attached to the original application.

Is the land properly zoned? Is a special use permit required?  What community outreach is required?  Please describe in detail your outreach plan?

The Glendale property, because it is located in an unincorporated section of the City of Glendale, is within the purview of Maricopa County as related to zoning. We have confirmed with Ms. Jen Pokowski, the Maricopa County Director of Planning and Development, that the Glendale property is properly zoned (commercial) and does not require a special use permit. No outreach for the purpose of seeking either zoning or special permitting is therefore deemed necessary.

We have confirmed that the Mesa property is properly zoned (commercial) but will require application to the City of Mesa for a special use permit. We have begun reaching out to the local community potentially affected by the construction and operation of our Secure Behavioral Health Residential Facility. In particular, this includes engagement and education of medical facility owners in buildings adjacent to our property and community members from Leisure World, a retirement community across Broadway Road to the south. In early discussions, both the medical facility owners and Community Manager of Leisure World have been supportive of the planned placement and operation of the Secure Behavioral Health Residential Facility. It should be noted that Copa Health has an existing relationship with Leisure World. For the last four years, Copa Health, through its subsidiary Marc Community Resources, Inc., has operated the Leisure World café as a job training program for individuals with serious mental illness.  The Leisure World residents have embraced the café operations and its trainees. In addition, Leisure World has donated its golf facilities to Marc Community Resources for fundraisers each of the last three years.

Outreach activities include:

Task 1:  Develop collateral materials regarding the new Secure BH Residential Facility, emphasizing the need for this facility, the security provisions, and the potential impact of this model on the delivery of BH care across the nation

Timeframe: These materials will be developed within 14 days of notice of grant award

Responsibility:  Marketing staff of Copa Health and Resilient Health

Task 2:  Meet with the full board of Leisure World regarding the planned Secure BH Residential Facility, providing an overview of the project, its purpose and programming, its significance as a demonstration project, and the onsite staffing and security measures that will be in place to ensure the safety of the nearby community

Timeframe: Meet with the Leisure World board of directors within 30 days of notice of AHCCCS grant award

Responsibility: Dr. Shar Najafi-Piper and Mr. Larry Villano, RHP Board Members

Who controls the building program and scope of work?

RHP, as the land and facility owner, will control the building program and accompanying scope of work. Copa Health and Resilient Health, as LLC member agencies and as contracted to manage the operation of the Secure BH Residential Facilities, will provide ongoing input to RHP in the building program and scope of work.

How does your firm plan to control costs?  What type of competition will there be through the procurement of subcontractors and building materials?

How does your firm plan to control costs?

The best opportunity to control construction costs comes in the design phase. The best way to get actual cost feedback in the design phase is by utilizing delivery methods that bring the design team and general contractor on board at the same time. We will use the Construction Manager at Risk (CMAR) project delivery method and generally follow the Arizona Revised Statues for Alternative Delivery Methods on public works projects. The use of CMAR will allow us to maintain the project design within the overall project budget and will result in a Guaranteed Maximum Price (GMP Not to Exceed) for the project. Our project manager has represented numerous public owners during their construction projects which used CMAR project delivery. They will monitor the details of project costs during construction to ensure value is received for all expended funds.

In addition, since the building design will be the same at both sites, we expect to will bundle both construction projects into one RFP to solicit competitive bids and evaluate submitted proposals based on credentials, costs, and other factors to select the best contractor for the two construction jobs. We will also involve a board member and subject matter expert in terms of designing functional and effective facilities in the assisted living, skilled nursing and dementia care space, which includes many similar features to a secure residential facility including, but not limited to the use of technology, and the need for security and effective designs to ensure program participants do not leave the facility inappropriately.

What type of competition will there be through the procurement of subcontractors and building materials?

By using the CMAR project delivery method, the CMAR will obtain multiple quotes for the subcontracting of labor and supply of materials for the construction. This will ensure competitive bidding of subcontractors and suppliers. Our project manager will oversee this process during the CMAR’s preparation of their GMP.

Since the construction costs are based on estimates, what additional funds are available to pay for any cost increases (in addition to any additional funds that were already identified in initial application)?  How will cost increases be handled?

RHP has set aside $228,000 on contingency funds to address unanticipated costs. These funds are in addition to funds already indicated in our initial application. Further, during the final building design phase to begin immediately after the grant is awarded, Copa Health and Resilient Health, as RHP LLC member agencies, will work closely together to make decisions that avoid overruns; both agencies are highly motivated to build two functional facilities for the least cost possible, without compromising the quality of the program or integrity of the building. Both agencies have combined $2 million line-of-credit and cash reserves sufficient to absorb additional costs and are committed to seeing this project to the finish line.

What is included in your estimate for FF&E?

A spreadsheet is attached with detailed information regarding the specific furniture, fixtures, and equipment required for this project, as well as the number required, cost per unit, vendor, and total cost.