## YH22-0009 Cost Proposal
Attachment A - Cost Proposal YH22-0009 - MES Modernization Roadmap Consultant
Phase | Major Deliverable | Deliverable Number (See Note A below) | Deliverable Description | Price | # of Calendar Days from Kickoff | Estimated Month/Year of Deliverable (MM/YYYY)
5.1 Kickoff Meeting | 5.1.1. Schedule and Narrative Workplan | 5.1.1 | Schedule and Narrative Workplan | 50000 | 23 days | 2021-12-24
5.2 Project Management | 5.2.1 Project Management Plan | 5.2.1 (a) | Project Management Plan Draft | 80000 | 41 days | 2022-01-11
|  | 5.2.1 (b) | Project Management Plan Approval | 40000 | 51 days | 2022-01-21
| 5.2.2 | 5.2.2 | Monthly Project Management Status Reports | 100000 | Status Reports will be submitted 10 days after the last day of the previous month.
5.3 Current State Assessment | 5.3.1 Current State Assessment Report | 5.3.1 (a) | Current State Assessment Report Draft | 445000 | 246 days | 2022-08-04
|  | 5.3.1 (b) | Current State Assessment Report Approval | 125000 | 266 days | 2022-08-24
5.4 Roadmap and Implementation Plan | 5.4.1 MES Modernization Roadmap | 5.4.1 (a) | MES Modernization Roadmap Draft | 275000 | 387 days | 2022-12-23
|  | 5.4.1 (b) | MES Modernization Roadmap Approval | 75000 | 407 days | 2023-01-12
5.4 Roadmap and Implementation Plan | 5.4.2 Implementation Plan | 5.4.2 (a) | Implementation Plan Draft | 50000 | 415 days | 2023-01-20
|  | 5.4.2 (b) | Implementation Plan Approval | 20000 | 435 days | 2023-02-09
5.5 MITA Assessments | 5.5.1 Arizona MITA-SSA | 5.5.1 (a) | MITA-SSA Report for Arizona Draft | 75000 | 581 days | 2023-07-05
|  | 5.5.1 (b) | MITA-SSA Report for Arizona Approval | 25000 | 601 days | 2023-07-25
| 5.5.2 Hawaii MITA-SSA | 5.5.2 (a) | MITA-SSA Report for Hawaii Draft | 75000 | 580 days | 2023-07-04
|  | 5.5.2 (b) | MITA-SSA Report for Hawaii Approval | 25000 | 600 days | 2023-07-24
5.6 Scopes of Work | 5.6.1 Scopes of Work | 5.6.1 | Scopes of Work (See Note B below) | $219/hour | NA | NA
5.7 Development of Specifications | 5.7.1 Requirements Traceability Matrix | 5.7.1 (a) | Requirements Traceability Matrix Draft | 25000 | 768 days | 2024-01-08
|  | 5.7.1 (b) | Requirements Traceability Matrix Approval | 10000 | 790 days | 2024-01-30
Notes:
(A) No travel is required for this contract.
(B) Since the number and types of Scopes of Work cannot be known at this phase, provide a blended hourly rate for development of Scopes of Work that will be used for fixed price amendments for each Scope of Work agreed to by both parties in future amendments to this contract. AHCCCS reserves the right to amend the pricing for future scopes of work to a more firm fixed price (deliverable based) depending on the situation and in collaboration with the Contractor.