## Updated w Key Staff Allocations
Attachment A - Cost Proposal YH22-0009 - MES Modernization Roadmap Consultant | [6 empty] | List out percent of resource allocation by deliverable to the project for all key personnel (examples shown below)
Phase | Major Deliverable | Deliverable Number (See Note A below) | Deliverable Description | Price | # of Calendar Days from Kickoff | Estimated Month/Year of Deliverable (MM/YYYY) | Jason Hargrove | Curtis Boyd | Ashley Zaldana | Kaela Stehly | Mir Ali | Elizabeth Jenkes | Jamie Champagne | Jennifer Webster | Shea Berry-Brennan | Brandon Milton
5.1 Kickoff Meeting | 5.1.1. Schedule and Narrative Workplan | 5.1.1 | Schedule and Narrative Workplan | 50000 | 23 days | 2021-12-24 | 55% | 27% | 31% | 31% | 8% | 3% | 3% | 0% | 8% | 4%
5.2 Project Management | 5.2.1 Project Management Plan | 5.2.1 (a) | Project Management Plan Draft | 80000 | 41 days | 2022-01-11 | 94% | 63% | 39% | 39% | 16% | 0% | 0% | 0% | 8% | 4%
|  | 5.2.1 (b) | Project Management Plan Approval | 40000 | 51 days | 2022-01-21 | 94% | 63% | 39% | 39% | 16% | 0% | 0% | 0% | 8% | 4%
| 5.2.2 | 5.2.2 | Monthly Project Management Status Reports | 100000 | monthly | monthly | 8% | 4% | 4% | 4% | 0% | 0% | 0% | 0% | 1% | 1%
5.3 Current State Assessment | 5.3.1 Current State Assessment Report | 5.3.1 (a) | Current State Assessment Report Draft | 445000 | 246 days | 2022-08-04 | 25% | 29% | 29% | 29% | 24% | 22% | 22% | 4% | 8% | 4%
|  | 5.3.1 (b) | Current State Assessment Report Approval | 125000 | 266 days | 2022-08-24 | 63% | 78% | 78% | 78% | 39% | 78% | 59% | 8% | 8% | 4%
5.4 Roadmap and Implementation Plan | 5.4.1 MES Modernization Roadmap | 5.4.1 (a) | MES Modernization Roadmap Draft | 275000 | 387 days | 2022-12-23 | 49% | 47% | 27% | 27% | 44% | 10% | 10% | 0% | 10% | 8%
|  | 5.4.1 (b) | MES Modernization Roadmap Approval | 75000 | 407 days | 2023-01-12 | 59% | 59% | 39% | 39% | 59% | 0% | 0% | 0% | 8% | 4%
5.4 Roadmap and Implementation Plan | 5.4.2 Implementation Plan | 5.4.2 (a) | Implementation Plan Draft | 50000 | 415 days | 2023-01-20 | 16% | 12% | 6% | 6% | 5% | 0% | 0% | 0% | 1% | 0%
|  | 5.4.2 (b) | Implementation Plan Approval | 20000 | 435 days | 2023-02-09 | 39% | 31% | 39% | 39% | 8% | 0% | 0% | 0% | 8% | 3%
5.5 MITA Assessments | 5.5.1 Arizona MITA-SSA | 5.5.1 (a) | MITA-SSA Report for Arizona Draft | 75000 | 581 days | 2023-07-05 | 16% | 16% | 5% | 5% | 4% | 4% | 4% | 0% | 2% | 1%
|  | 5.5.1 (b) | MITA-SSA Report for Arizona Approval | 25000 | 601 days | 2023-07-25 | 23% | 23% | 12% | 12% | 8% | 4% | 4% | 0% | 4% | 2%
| 5.5.2 Hawaii MITA-SSA | 5.5.2 (a) | MITA-SSA Report for Hawaii Draft | 75000 | 580 days | 2023-07-04 | 16% | 16% | 5% | 5% | 4% | 4% | 4% | 0% | 2% | 1%
|  | 5.5.2 (b) | MITA-SSA Report for Hawaii Approval | 25000 | 600 days | 2023-07-24 | 23% | 23% | 12% | 12% | 8% | 4% | 4% | 0% | 4% | 2%
5.6 Scopes of Work | 5.6.1 Scopes of Work | 5.6.1 | Scopes of Work (See Note B below) | $219/hour | na | na | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
5.7 Development of Specifications | 5.7.1 Requirements Traceability Matrix | 5.7.1 (a) | Requirements Traceability Matrix Draft | 25000 | 768 days | 2024-01-08 | 16% | 16% | 31% | 31% | 0% | 0% | 0% | 0% | 4% | 2%
|  | 5.7.1 (b) | Requirements Traceability Matrix Approval | 10000 | 790 days | 2024-01-30 | 8% | 4% | 8% | 8% | 0% | 0% | 0% | 0% | 4% | 2%
|  |  |  | 1495000 | 790 | na
|  |  |  | Total Price | Total # Days
Notes:
(A) No travel is required for this contract.
(B) Since the number and types of Scopes of Work cannot be known at this phase, provide a blended hourly rate for development of Scopes of Work that will be used for fixed price amendments for each Scope of Work agreed to by both parties in future amendments to this contract. AHCCCS reserves the right to amend the pricing for future scopes of work to a more firm fixed price (deliverable based) depending on the situation and in collaboration with the Contractor.
BerryDunn Notes:
We have provided additional columns to show the resource allocation of key staff across all deliverables, shown as a percentage of their time dedicated to that deliverable. We have also provided some key considerations for reviewing these percent allocations:
a) The percent allocation was determined by dividing the number of hours assigned to the key staff member for the development of the deliverable, divided by the approximate number of months allocated to the development of the deliverable in the project schedule, divided by 128 hours, which is an average monthly full time equivalent (FTE).
b) Several deliverables overlap in the project schedule and therefore the percent allocations can be deceiving. The allocation for one deliverable may be small for that period of time, but that resource is fully allocated to the project during that same period because they are working on multiple, concurrent deliverables.
c) The percent allocation for some major deliverables may seem small because content that is developed in prior deliverables will be leveraged for subsequent deliverables, e.g. a lot of the content developed for the Current State Assessment will inform the updates to the two MITA-SSA Reports. Note: The cost for those deliverables reflects this efficiency as well.
d) The time allocated to some deliverables in the project schedule may be several months, however the majority of the work for the deliverable may be condensed to a small subset of those months, which will distort the percent allocations when using the formula described in a) above. For example, the Current State Assessment will take place over 8 months so the percent allocations look small, but in reality several key staff will be working full-time on this deliverable during the information gathering activities and the business process mapping effort.
e) Note: the days in the Cost Proposal are calendar days and the dates in the Project Plan are business days.