## Updated w Key Staff Allocations
Attachment A - Cost Proposal YH22-0009 - MES Modernization Roadmap Consultant | [6 empty] | List out percent of resource allocation by deliverable to the project for all key personnel (examples shown below)
Phase | Major Deliverable | Deliverable Number (See Note A below) | Deliverable Description | Price | # of Calendar Days from Kickoff | Estimated Month/Year of Deliverable (MM/YYYY) | Paul Brannan, PMP HIT PM Consultant | Laura Larimer HIT Senior Consultant | Chris Smith HIT Technical Data Architect | Denise Fuson HIT Analyst
5.1 Kickoff Meeting | 5.1.1. Schedule and Narrative Workplan | 5.1.1 | Schedule and Narrative Workplan | 7150 | 30 days | October 2021 | 100% | 15% | 15% | 15%
5.2 Project Management | 5.2.1 Project Management Plan | 5.2.1 (a) | Project Management Plan Draft | 14445 | 45 days | November 2021 | 100% | 15% | 15% | 15%
|  | 5.2.1 (b) | Project Management Plan Approval | 5000 | 15 days | November 2021 | 100% | 5% | 5% | 5%
| 5.2.2 | 5.2.2 | Monthly Project Management Status Reports | 4860 | Ongoing throughout the project | March 2023 | 100% | 5% | 5% | 5%
5.3 Current State Assessment | 5.3.1 Current State Assessment Report | 5.3.1 (a) | Current State Assessment Report Draft | 390900 | 210 days | May 2022 | 20% | 100% | 100% | 100%
|  | 5.3.1 (b) | Current State Assessment Report Approval | 20812.5 | 30 days | June 2022 | 5% | 100% | 100% | 100%
5.4 Roadmap and Implementation Plan | 5.4.1 MES Modernization Roadmap | 5.4.1 (a) | MES Modernization Roadmap Draft | 292930 | 180 days | November 2022 | 20% | 100% | 100% | 100%
|  | 5.4.1 (b) | MES Modernization Roadmap Approval | 16547.75 | 30 days | December 2022 | 5% | 100% | 100% | 100%
5.4 Roadmap and Implementation Plan | 5.4.2 Implementation Plan | 5.4.2 (a) | Implementation Plan Draft | 232005 | 180 days | November 2022 | 40% | 100% | 100% | 100%
|  | 5.4.2 (b) | Implementation Plan Approval | 13501.5 | 30 days | December 2022 | 100% | 100% | 100% | 100%
5.5 MITA Assessments | 5.5.1 Arizona MITA-SSA | 5.5.1 (a) | MITA-SSA Report for Arizona Draft | 140795 | 120 days | August 2022 | 20% | 75% | 100% | 100%
|  | 5.5.1 (b) | MITA-SSA Report for Arizona Approval | 9236.75 | 30 days | September 2022 | 5% | 75% | 100% | 100%
| 5.5.2 Hawaii MITA-SSA | 5.5.2 (a) | MITA-SSA Report for Hawaii Draft | 128610 | 120 days | August 2022 | 20% | 75% | 100% | 100%
|  | 5.5.2 (b) | MITA-SSA Report for Hawaii Approval | 8627.5 | 30 days | September 2022 | 5% | 75% | 100% | 100%
5.6 Scopes of Work | 5.6.1 Scopes of Work | 5.6.1 | Scopes of Work (See Note B below) | $150 per hour | NA | NA | TBD | TBD | TBD | TBD
5.7 Development of Specifications | 5.7.1 Requirements Traceability Matrix | 5.7.1 (a) | Requirements Traceability Matrix Draft | 90365 | 400 days | January 2023 | 20% | 50% | 50% | 100%
|  | 5.7.1 (b) | Requirements Traceability Matrix Approval | 6799.75 | 50 days | February 2023 | 5% | 100% | 100% | 100%
|  |  |  | 1382585.75 | 1500 Days(overlapping) *estimated total duration of 18 months | na
|  |  |  | Total Price | Total # Days
Notes:
(A) No travel is required for this contract.
(B) Since the number and types of Scopes of Work cannot be known at this phase, provide a blended hourly rate for development of Scopes of Work that will be used for fixed price amendments for each Scope of Work agreed to by both parties in future amendments to this contract. AHCCCS reserves the right to amend the pricing for future scopes of work to a more firm fixed price (deliverable based) depending on the situation and in collaboration with the Contractor.
(C) Based on an 18 month duration, with an anticipated start date of October 1, 2021
(D) HIT Senior Consultant, HIT Technical Data Archtiect, and HIT Analyst are full-time dedicated resources to this effort for a duration of 18 months
(E) HIT PM Consultant would be a half-time dedicated resource to this effort for a duration of 18 months