## Sheet1
Detailed Timeline for YH22-0009, MES Modernization Roadmap Consultant RFP
Prepared by: Briljent
Durations are listed in business days
Task Name | Duration | Start | Finish
Contract Award/Project Start Date |  | 2021-10-01
5.1 - Kickoff Meeting
Internal Briljent Team Planning and Project Set up | 5 days | 2021-10-04 | 2021-10-08
Schedule AHCCCS and MQD - Briljent Kickoff Meeting | 1 day | 2021-10-07 | 2021-10-08
Draft Project Schedule and Narrative Workplan | 3 days | 2021-10-11 | 2021-10-13
Briljent Team QA Schedule and Workplan | 1 day | 2021-10-14 | 2021-10-14
Draft Kickoff Meeting Agenda | 1 day | 2021-10-14 | 2021-10-14
Submit Draft Schedule, Workplan, and Kickoff Meeting Agenda to AHCCCS/MQD Project Managers | 0 day | 2021-10-15 | 2021-10-15
Conduct Kickoff Meeting | 1 day | 2021-10-20 | 2021-10-22 | Kickoff meeting will occur within this date range
Develop and Submit Kickoff Meeting Notes | 2 days | 2021-10-25 | 2021-10-26
Receive AHCCCS/MQD Edits to Project Schedule and Workplan | 3 days | 2021-10-25 | 2021-10-27
Revise Project Schedule and Narrative Workplan | 2 days | 2021-10-28 | 2021-10-29
Submit Deliverable 5.1.1: Final Schedule and Narrative Workplan | 0 day | 2021-11-01 | 2021-11-01
Deliverable Approval - Project Schedule and Workplan | 5 days | 2021-11-08 | 2021-11-08
Prepare Materials and Schedule State Orientation Session | 8 days | 2021-10-08 | 2021-10-19
Conduct State Orientation Session with AHCCCS/MQD Staff | 1 day | 2021-10-25 | 2021-10-29 | Orientation session will occur within this date range
5.2 Project Management
Develop Project Management Plan | 6 days | 2021-10-25 | 2021-11-01
Briljent Team QA Project Management Plan | 2 days | 2021-11-02 | 2021-11-03
Submit Draft Project Management Plan | 0 day | 2021-11-05 | 2021-11-05
Receive AHCCCS and MQD Edits to Project Management Plan | 5 days | 2021-11-08 | 2021-11-12
Revise Project Management Plan | 2 days | 2021-11-15 | 2021-11-16
Submit Deliverable 5.2.1: Final Project Management Plan | 0 day | 2021-11-17 | 2021-11-17
Deliverable Approval - Project Management Plan | 5 days | 2021-11-18 | 2021-11-24
Draft and Submit Agendas for Weekly Status Meetings | Ongoing throughout project | 2021-10-25 | 2023-03-17 | Weekly meetings to begin following the Kickoff Meeting
Conduct Weekly Status Meetings | Ongoing throughout project | 2021-11-01 | 2023-03-24
Prepare and Send Status Meeting Notes | Ongoing throughout project | 2021-11-05 | 2023-03-31
Prepare and Briljent Team Review of Deliverable Expectation Documents (DEDs) | 15 days | 2021-10-25 | 2021-11-12
Submit DEDs to AHCCCS/MQD Project Managers | 0 day | 2021-11-15 | 2021-11-15
Prepare Monthly Project Management Status Reports | 2 days each month; ongoing throughout project | 2021-10-26 | 2023-03-31
Briljent Team QA Monthly Status Reports | 1 day each month; ongoing throughout project | 2021-10-28 | 2023-03-31
Submit Deliverable 5.2.2: Monthly Project Management Status Reports | Submit by 3rd business day following each month end | 2021-11-03 | 2023-03-31 | Will submit final report by project completion date
Deliverable Approval - Monthly Status Reports | Due 5 business days following each monthly submission | 2021-11-10 | 2023-04-07
5.3 - Current State Assessment
Background Research and a Review of MQD and AHCCCS Programs | 20 days | 2021-11-01 | 2021-11-30 | Accounts for Thanksgiving and Day After Thanksgiving Holidays
Prepare For and Conduct Interviews and Small Group Meetings | 23 days | 2021-11-15 | 2021-12-17
Create and Disseminate Surveys to Various Staffing Areas | 23 days | 2021-11-15 | 2021-12-17
Compile and Reviewing Findings from Interviews and Surveys | 12 days | 2021-12-20 | 2022-01-07 | Accounts for Christmas Eve, Christmas Day, and New Year's Day Holidays
Review Current Business Process Documentation | 16 days | 2022-01-10 | 2022-01-31
Conduct Technology Assessment | 45 days | 2022-02-01 | 2022-03-31
Technical Architecture | These topic areas will be reviewed and evaluated as part of the technology assessment
Information Architecture
Technical Integration Points
CMS Final Rule (9115-F)
Hosting Environment Assessment
Conduct Risk Assessment | 23 days | 2022-03-01 | 2022-03-31
Conduct Staff Skills Assessment | 30 days | 2021-04-01 | 2022-05-13 | Accounts for Good Friday Holiday
Draft Current State Assessment Report | 15 days | 2022-05-16 | 2022-06-06 | Accounts for Memorial Day Holiday
Briljent Team QA Draft Current State Report | 3 days | 2022-06-07 | 2022-06-09
Submit Draft Current State Assessment Report | 0 day | 2022-06-10 | 2022-06-10
Receive AHCCCS and MQD Edits to Draft Current State Assessment Report | 7 days | 2022-06-13 | 2022-06-21
Revise Current State Assessment Report | 4 days | 2022-06-22 | 2022-06-27
Submit Deliverable 5.3.1: Final Current State Assessment Report | 0 day | 2022-06-28 | 2022-06-28
Deliverable Approval - Current State Assessment Report | 5 days | 2022-06-29 | 2022-07-06 | Accounts for Independence Day Holiday
5.4 - MES Modernization Roadmap and Implementation Plan
Discuss and Document Goals and Objectives for AHCCCS and MQD | 5 days | 2022-06-06 | 2022-06-10
Develop Future State Recommendations | 49 days | 2022-06-13 | 2022-08-19 | Accounts for Independence Day Holiday
Rules Management and Information Architecture | These topic areas will be included in the recommendations that are developed for AHCCCS and MQD.
Central Control and Environment Monitor
Cloud Environment and Cloud Hosting
Storage, ESB, Web-services and Standards, SOA
Data Formats and Data Processing
Recommended Toolsets
Data Migration Plan
Disaster Recovery and Business Continuity Plan
Prepare Gap Analysis Table | 8 days | 2022-08-22 | 2022-08-31
Conduct Cost Benefit Analysis on Recommendations and Assess ROI | 11 days | 2022-09-01 | 2022-09-16 | Accounts for Labor Day Holiday
Compile Strategic Priorities | 10 days | 2022-09-19 | 2022-09-30
Prepare Presentation with Strategic Priorities and Key Recommendations | 8 days | 2022-09-28 | 2022-10-07
Conduct State Presentation and Confirm Key Recommendations | 2 days | 2022-10-10 | 2022-10-13 | State Presentation will occur within this date range | Accounts for Columbus Day Holiday
Draft MES Modernization Roadmap | 12 days | 2022-10-14 | 2022-10-31
Briljent Team QA MES Modernization Roadmap | 4 days | 2022-11-01 | 2022-11-04
Submit Draft MES Modernization Roadmap | 0 day | 2022-11-07 | 2022-11-07
Receive AHCCCS and MQD Edits to Draft MES Modernization Roadmap | 7 days | 2022-11-08 | 2022-11-17 | Accounts for Veterans Day Holiday
Revise MES Modernization Roadmap | 4 days | 2022-11-18 | 2021-11-25 | Accounts for Thanksgiving and Day After Thanksgiving Holidays
Submit Deliverable 5.4.1: Final MES Modernization Roadmap | 0 day | 2022-11-28 | 2022-11-28
Deliverable Approval - Final MES Modernization Roadmap | 7 days | 2022-11-29 | 2022-12-07
Draft Implementation Plan | 13 days | 2022-11-08 | 2022-11-29 | Accounts for Veterans Day, Thanksgiving, and Day After Thanksgiving Holidays
Briljent Team QA Draft Implementation Plan | 3 days | 2022-11-30 | 2022-12-02
Submit Draft Implementation Plan | 0 day | 2022-12-05 | 2022-12-05
Receive AHCCCS and MQD Edits to Draft Implementation Plan | 6 days | 2022-12-06 | 2022-12-13
Revise Implementation Plan | 5 days | 2022-12-14 | 2022-12-20
Submit Deliverable 5.4.2: Final Implementation Plan | 0 day | 2022-12-21 | 2022-12-21
Deliverable Approval - Final Implementation Plan | 6 days | 2022-12-22 | 2023-01-03 | Accounts for Christmas Eve, Christmas Day, and New Year's Day Holidays
5.5 - MITA Assessments
Review Current State Assessment and Conduct Remaining Background Research and Documentation Review (As Needed) | 15 days | 2022-05-02 | 2022-05-20
Review 2016 AHCCCS SS-A and 2019 MQD SS-A | 20 days | 2022-05-02 | 2022-05-27
Conduct Additional Staff/Stakeholder Interviews (As Needed) | 15 days | 2022-05-09 | 2022-05-27
Draft MITA-SSA Report for Arizona | 24 days | 2022-05-31 | 2022-07-01
Draft MITA-SSA Report for Hawaii | 24 days | 2022-06-06 | 2022-07-08 | Accounts for Independence Day Holiday
Briljent Team QA MITA-SSA Reports | 5 days | 2022-07-11 | 2022-07-15
Submit Draft MITA-SSA Report to AHCCCS | 0 day | 2022-07-18 | 2022-07-18
Submit Draft MITA-SSA Report to MQD | 0 day | 2022-07-18 | 2022-07-18
Receive Edits to Draft MITA-SSA Reports | 7 days | 2021-07-19 | 2022-07-27
Revise MITA-SSA Reports | 6 days | 2021-07-28 | 2022-08-04
Submit Deliverable 5.5.1: Final MITA-SSA Report for Arizona | 0 day | 2022-08-05 | 2022-08-05
Submit Deliverable 5.5.2: Final MITA-SSA Report for Hawaii | 0 day | 2022-08-05 | 2022-08-05
Deliverable Approval - Final MITA-SSA Report for Arizona | 7 days | 2022-08-08 | 2022-08-16
Deliverable Approval - Final MITA-SSA Report for Hawaii | 7 days | 2022-08-08 | 2022-08-16
5.7 - Development of Specifications
Develop Requirements Traceability Matrix Template | 7 days | 2021-12-01 | 2021-12-09
Submit Matrix Template to AHCCCS and MQD for Approval | 0 day | 2021-12-10 | 2021-12-10
Track and Log Requirements Monthly Into Template | Monthly, throughout the project | 2021-12-13 | 2023-02-08
Prepare Complete Requirements Traceability Matrix | 5 days | 2023-02-09 | 2023-02-15
Submit Draft Requirements Traceability Matrix to AHCCCS and MQD | 0 day | 2023-02-16 | 2023-02-16
Receive Edits to Draft Requirements Traceability Matrix | 3 days | 2023-02-17 | 2023-02-21
Revise Requirements Traceability Matrix | 2 days | 2023-02-22 | 2023-02-23
Submit Deliverable 5.7.1: Final Requirements Traceability Matrix | 0 day | 2023-02-24 | 2023-02-24
Deliverable Approval - Final Requirements Traceability Matrix | 2 days | 2023-02-27 | 2023-02-28 | Shorter review as AHCCCS and MQD would have been able to review the Matrix throughout the project.
5.6 - Optional Scopes of Work | TBD | TBD | TBD
Project End Date |  | 2023-03-31 | 2023-03-31