## Updated w Key Staff Allocations
Attachment A - Cost Proposal YH22-0009 - MES Modernization Roadmap Consultant | [6 empty] | List out percent of resource allocation by deliverable to the project for all key personnel (examples shown below)
Phase | Major Deliverable | Deliverable Number (See Note A below) | Deliverable Description | Price | # of Calendar Days from Kickoff | Estimated Month/Year of Deliverable (MM/YYYY) | Key Staff #1 (Kim Smith) | Key Staff #2 (Brad Perrin) | Key Staff #3 (Gina Austin) | Key Staff #4 (Gay Munyon)
5.1 Kickoff Meeting | 5.1.1. Schedule and Narrative Workplan | 5.1.1 | Schedule and Narrative Workplan | 32526 | 30 | 2021-12-31 | 100% | 0% | 5% | 5%
5.2 Project Management | 5.2.1 Project Management Plan | 5.2.1 (a) | Project Management Plan Draft | 63889 | 61 | 2022-01-31 | 100% | 0% | 5% | 0%
|  | 5.2.1 (b) | Project Management Plan Approval | 52273 | 89 | 2022-02-28 | 100% | 0% | 0% | 0%
| 5.2.2 | 5.2.2 | Monthly Project Management Status Reports | 320606 | Monthly | $24,662 per month | 10% | 0% | 5% | 0%
5.3 Current State Assessment | 5.3.1 Current State Assessment Report | 5.3.1 (a) | Current State Assessment Report Draft | 162626 | 211 | 2022-06-30 | 90% | 100% | 5% | 5%
|  | 5.3.1 (b) | Current State Assessment Report Approval | 58081 | 242 | 2022-07-31 | 90% | 100% | 0% | 0%
5.4 Roadmap and Implementation Plan | 5.4.1 MES Modernization Roadmap | 5.4.1 (a) | MES Modernization Roadmap Draft | 121970 | 334 | 2022-10-31 | 90% | 100% | 5% | 5%
|  | 5.4.1 (b) | MES Modernization Roadmap Approval | 34849 | 364 | 2022-11-30 | 90% | 0% | 0% | 0%
5.4 Roadmap and Implementation Plan | 5.4.2 Implementation Plan | 5.4.2 (a) | Implementation Plan Draft | 81313 | 364 | 2022-11-30 | 90% | 100% | 5% | 5%
|  | 5.4.2 (b) | Implementation Plan Approval | 34849 | 395 | 2022-12-31 | 90% | 0% | 0% | 0%
5.5 MITA Assessments | 5.5.1 Arizona MITA-SSA | 5.5.1 (a) | MITA-SSA Report for Arizona Draft | 52273 | 364 | 2022-11-30 | 5% | 10% | 5% | 0%
|  | 5.5.1 (b) | MITA-SSA Report for Arizona Approval | 18586 | 395 | 2022-12-31 | 90% | 0% | 0% | 0%
| 5.5.2 Hawaii MITA-SSA | 5.5.2 (a) | MITA-SSA Report for Hawaii Draft | 52273 | 364 | 2022-11-30 | 5% | 10% | 5% | 0%
|  | 5.5.2 (b) | MITA-SSA Report for Hawaii Approval | 18586 | 395 | 2022-12-31 | 90% | 0% | 0% | 0%
5.6 Scopes of Work | 5.6.1 Scopes of Work | 5.6.1 | Scopes of Work (See Note B below) | Not-to-Exceed $251.00 per hour | NA | NA | NA | NA | NA | NA
5.7 Development of Specifications | 5.7.1 Requirements Traceability Matrix | 5.7.1 (a) | Requirements Traceability Matrix Draft | 32526 | 364 | 2022-11-30 | 90% | 0% | 0% | 0%
|  | 5.7.1 (b) | Requirements Traceability Matrix Approval | 24394 | 395 | 2022-12-31 | 90% | 0% | 0% | 0%
|  |  |  | 1161620 | 420 | na
|  |  |  | Total Price | Total # Days
| Notes: | [7 empty] | 148688
[9 empty] | 24662 | 296660
| (A) No travel is required for this contract. | [8 empty] | 692326 | 864960
(B) Since the number and types of Scopes of Work cannot be known at this phase, provide a blended hourly rate for development of Scopes of Work that will be used for fixed price amendments for each Scope of Work agreed to by both parties in future amendments to this contract. AHCCCS reserves the right to amend the pricing for future scopes of work to a more firm fixed price (deliverable based) depending on the situation and in collaboration with the Contractor.