1. Pertaining to your proposed project schedule (see Special Instructions to Offerors #5.2.3):

- Please provide a detailed explanation for the length of time proposed in your timeline, preferably focusing on the larger deliverables such as MES Roadmap Approval and MITA Approvals for both states.

It has been PCG’s experience that a typical SS-A effort requiring significant updates with minimal re-use of existing material will require approximately 9-12 months of effort utilizing dedicated PCG staff experienced in the SS-A effort. Given that this effort will involve completing two SS-As, we estimate the overall timeline for this to be 12 months from start to finish. In past engagements, PCG staff will need to schedule and meet with numerous SMEs in order to complete the analysis for both business and technical domains. PCG has a defined and mature process for completing SS-As and our experience and judgment was factored into our estimates. All phase durations were based on historical projects.

In a recent SS-A engagement for the Commonwealth of KY, PCG completed a modified SS-A (updating only the “To-Be” environment first) in approximately 6-7 months in order to support the state’s certification timeline. The additional work to update the “As-Is” state completely was completed in an additional 3 months. The time to complete this work incorporates our experience with securing timely resources, allowing for various SMEs and stakeholders review time, and includes multiple iterations of review/refinement that is required for a complete assessment. We also considered AHCCCS’ RFP clarifying comments stating that much of the current material will not be re-usable.

PCG has planned for staff to operate simultaneously on the AZ and HI SS-A efforts, and we will leverage some commonalities between the two states for efficiency as well as to minimize where possible the involvement of state resources. Our standard assessment approach assigns a dedicated lead PM/SME to each SS-A effort as well as a Sr. MES Technical Architect, several analysts, and other SMEs as needed. These resources operate as a dedicated project team for the duration of the effort and will be available after completion for adjustments or follow ups.

The following table highlights several key milestones based on our proposed schedule and provides additional details for each of the key areas.

| Summary of Key Milestones in PCG’s proposed Project Schedule |  |  |  |  |
| --- | --- | --- | --- | --- |
| Deliverable Name | Start Date (Task #) | Interim Deliverable Date | End Date (Task #) | Explanation regarding Timeline |
| MES Roadmap Approval | 12/21 (Task 127) | 7/22 *After completion of the “To-Be” assessment milestone (Task 161) | 12/22 (Task 193) | Much of the work (data gathering) PCG does on the Roadmap deliverable will be largely completed by July 2022. The final completion end date of December 2022 in our project schedule reflects the final updates/adjustments that are anticipated once all requirements have been collected and vetted through the RTM. PCG can provide interim results on the Roadmap and preliminary recommendations as early as July 2022. Our schedule was built with the final Roadmap deliverable being dependent on predecessor work such as the completion of the individual SS-A deliverables (Tasks #179-186 in our project schedule). We would expect that critical information from those deliverables will need to be assessed for a final Roadmap recommendation. While the dates for drafting and approving the Roadmap are identified over a one-month period, we anticipate that discussions with AHCCCS leadership and key stakeholders will be on-going throughout the engagement. These discussions will be important to understand the Agency’s vision and driving factors for the Roadmap. |
| Current State Assessment | 11/21 (Task 120) | NA | 6/10/22 (Task 143) | PCG’s process for SS-A development includes a Current State Assessment (covers both AZ and HI) and can be presented as an interim deliverable as part of the overall SS-A effort. |
| AZ MITA SS-A | 6/22 (Task 144) | 9/22 (Task 173) MITA Maturity Roadmap | 11/22 (Task 185) | This phase of the SS-A process focuses on defining the “To-Be” state for the AZ MES. Includes completion of a gap analysis and completes the Concept of Operations (interim deliverable). Much of the individual AZ SS-A will be completed by September 2022 and interim deliverable for the MITA Maturity Roadmap will be complete at that time. **Note: AZ and HI efforts are being done simultaneously |
| HI MITA SS-A | 6/22 (Task 144) | 9/22 (Task 173) MITA Maturity Roadmap | 11/22 (Task 186) | This phase of the SS-A process focuses on defining the “To-Be” state for HI MES. Includes completion of a gap analysis and completes the Concept of Operations (interim deliverable). Much of the individual HI SS-A will be completed by September 2022 and interim deliverable for the MITA Maturity Roadmap will be complete at that time. **Note: AZ and HI efforts are being done simultaneously |

- Please also include the number of proposed staff, with positions, and level of effort assigned to the project. Please also include assumptions for state resources needed to contribute to the project.

- Proposed staff and allocation for each Deliverable has been included in the revised Cost Estimate spreadsheet (attached).

- In our Technical Proposal, PCG has provided detailed steps that will be carried out during the Project which will involve state resources. These activities include the project kickoff, individual and group interviews, strategy discussions to determine business drivers and vision, documentation gathering activities to identify existing information repositories, and deliverable reviews and approvals. Each activity in our approach includes the affected stakeholders and expected involvement, which is typically to review the pre-meeting agendas and questions that PCG sends out, and to be active and timely participants in discussions. To summarize the state resources which will be needed, AHCCCS can expect to involve:

- AHCCCS leadership

- Business Unit/Process owners

- Database Administrators (DBAs) for appropriate datastores

- Anyone who manages the relationships/interfaces between business units or systems

- Case managers (people who actually use the system to do the work)

- IT support staff directly responsible for the system

These resources will be engaged heavily in planned workshops during the current state assessment and individual SS-A phases of the project. These resources will also be engaged at various ad-hoc points during the project to refine the overall Roadmap strategy.

- Please resubmit your cost proposal with additional columns describing the resource allocation of key staff (see attached). You may not alter any of the prices from the initial proposal submitted.

- Proposed staff and allocation for each Deliverable has been included in the revised Cost Estimate spreadsheet  (attached).

- PCG intends to deploy a fully prepared, deeply knowledgeable, and highly enthusiastic group of professionals who work well together and have a proven track record of assisting HHS agencies with initiatives of similar size and scope. The staffing plan for this project is distinctive for the multiple and well-developed skillsets that will be applied to assist with the developing a Roadmap and fully developed SS-A for the AHCCCS projects described in the RFP. In addition, we have chosen staff with significant experience managing modularity initiatives for state Medicaid agencies.

2. Pursuant to Scope of Work Requirement ID PM-006/Project Management, the State has outlined the minimum requirements for resource replacement. Please provide your detailed process for resource replacement. If you have already included it in your proposal, please restate it in your clarification.

The proposed PCG staff for the AZ MES Roadmap effort are current employees of PCG and will be allocated to the AZ MES project (assuming proposed contract award on or about 1 October 2021). PCG agrees to the stated processes outlined in section PM-006 of the RFP.

| PM-006 | Project Management | The state shall approve all resources assigned to the project. In the event the Contractor needs to replace any resource, such requests shall be submitted ten (10) business days in advance of the replacement taking effect. The Contractor's Key Personnel positions may not be vacant for more than ten (10) business days without a qualified substitute (temporary replacement). A qualified substitute shall be in place no more than ten (10) business days after the separation date of the vacating resource. The definition of a qualified substitute is someone meeting the requirements of the RFP. AHCCCS reserved the right to deny the proposed replacement if they do not meet the qualifications. |
| --- | --- | --- |

PCG understands the importance of maintaining continuity of effort if resources are replaced. The PCG Program Manager has access to the full breadth of PCG resources and recruiters throughout the nation should the need arise to replace or add staff to meet increased project demand. PCG has a deep pool of resources across the country with specialized Medicaid and healthcare knowledge that can be pulled into the project on short notice to help ensure task deadlines are met. The Program Manager will meet both regularly and periodically with AHCCCS to ensure PCG is providing the highest quality services. Should the need arise to bring on additional/replacement project staff, the Program Manager will acquire staff that meets specific qualifications.

Transitioning Work

The PCG team consists of individuals with expertise in a multitude of areas. They also partner together to make sure all work is covered thoroughly, with quality, and with objectivity. This approach provides a model that allows for the seamless transitioning of work should a person be replaced or unavailable for a length of time. PCG will not have any individual fill more than one Key Personnel role but will cross-train staff to support each other and the work effort during times of transition. In addition, regular communication between AHCCCS and the Program Manager will be used to proactively address staffing concerns and needs, allowing time for one person to orient their replacement when possible.

If a change must be made to one of PCG’s key personnel, we will notify AHCCCS at least ten (10) business days in advance of the change to inform them of the reason for the change and the proposed replacement, along with their resume. We understand that all substitutions are subject to AHCCCS approval.

PCG’s replacement process in the event proposed staff are not available or subsequently leave PCG is as follows:

- PCG’s first approach will be to allocate similarly skilled staff from within PCG. We have identified internal PCG back-up personnel for each of the Key positions we are providing staff for.

  - By contracting with PCG, AHCCCS will also gain access to our deep bench of HHS subject matter experts and consultants that comprise our traditional consulting practice. Across our Health, Human Services, and Technology Consulting Practice Areas, PCG employs over hundreds of staff who possess expertise relevant to the project scope. PCG will access that pool of resources anytime necessary to ensure that AHCCCS has the right people on the project teams.

- All replacement resumes will be sent to AHCCCS for approval.

- We will adhere to the defined process outlined in PM-006 for required timeframes.