## Submitted Cost Proposal
Vendor Name: HealthTech Solutions, LLC
YH23-0021 Arizona System Integrator
Total Contract Price
SI Platform Design, Development, and Implementation | 8513793.48
Maintenance and Operations - Year 1 | 4637011.54
Maintenance and Operations - Year 2 | 5332563.27
Maintenance and Operations - Year 3 | 6132447.76
Maintenance and Operations - Year 4 | 7052314.92
Modification Hours | 14926500
Total Contract Value (Year 1 - Year 5) | 46594630.97
`

## Payment Invoice Schedule - DDI
Vendor Name: HealthTech Solutions, LLC
YH23-0021 Arizona System Integrator
Estimated Invoice Schedule - DDI
| DDI Contract Period | Contract Period: 1 Year |  |  | Mod Hourly Rate | 165.85
Project Month Invoiced | Invoice Number (Invoice Submission Frequency - Monthly) | Deliverable Cost | Fixed Fee Cost | Estimated Modification Pool Hours | Estimated Modification Pool Cost | Total Estimated Invoice Amount | Deliverables Included as Deliverable Based Cost
2023-07-23 | 1 | 42568.9674 | 0 | 0 |  | 42568.9674 | DEL-07: Project Management Repository (PMR)
2023-08-23 | 2 | 808810.3806 | 0 | 0 |  | 808810.3806 | DEL-02: Project Management Plan DEL-04: Change Management and Modification Pool Plan (ChMP) DEL-06: Risk Management Plan (RMP) DEL-019: Project Schedule
2023-09-23 | 3 |  | 766241.4132 | 0 |  | 766241.4132
2023-10-23 | 4 |  | 766241.4132 | 2500 | 414625 | 1180866.4132
2023-11-23 | 5 |  | 766241.4132 | 2500 | 414625 | 1180866.4132
2023-12-23 | 6 |  | 766241.4132 | 2500 | 414625 | 1180866.4132
2023-01-24 | 7 |  | 766241.4132 | 2500 | 414625 | 1180866.4132
2023-02-24 | 8 |  | 766241.4132 | 2500 | 414625 | 1180866.4132
2023-03-24 | 9 |  | 766241.4132 | 2500 | 414625 | 1180866.4132
2023-04-24 | 10 |  | 766241.4132 | 2500 | 414625 | 1180866.4132
2023-05-24 | 11 |  | 766241.4132 | 2500 | 414625 | 1180866.4132
2023-06-24 | 12 |  | 766241.4132 | 2500 | 414625 | 1180866.4132
| Total Invoiced Amount | 851379.348 | 7662414.132 | 22500 | 3731625 | 12245418.48

## Payment Invoice Schedule - O&M
Vendor Name: HealthTech Solutions, LLC
YH23-0021 Arizona System Integrator
Operations and Maintanence Estimated Invoice Amounts
(Note: To be billed and invoiced on monthly basis as fixed monthly fee for O&M services)
|  |  |  | Mod Hourly Rate | 165.85
|  | Annual Total Fixed Cost | Monthly Invoice Amount (Fixed) | Annual Est. Modification Hours | Annual Est. Modification Pool Cost | Est. Monthly Invoice Amount - Modification Pool | Annual Total Cost (Fixed Cost + Mod Hours) | Est. Invoice Monthly Total
| Maintenance and Operations - Year 1 | 4637011.54 | 386417.6283 | 27000 | 4477950 | 373162.5 | 9114961.54 | 759580.1283
| Maintenance and Operations - Year 2 | 5332563.27 | 444380.2725 | 13500 | 2238975 | 186581.25 | 7571538.27 | 630961.5225
| Maintenance and Operations - Year 3 | 6132447.76 | 511037.3133 | 13500 | 2238975 | 186581.25 | 8371422.76 | 697618.5633
| Maintenance and Operations - Year 4 | 7052314.92 | 587692.91 | 13500 | 2238975 | 186581.25 | 9291289.92 | 774274.16
Monthly Invoice Amounts
| Project Month Invoiced | Invoice Number (Invoice Submission: Monthly) | Fixed fee cost | Estimated Modification Pool Cost | Total Estimated Invoice Amount
| 2024-07-01 | 13 | 386417.6283 | 373162.5 | 759580.1283
| 2024-08-01 | 14 | 386417.6283 | 373162.5 | 759580.1283
| 2024-09-01 | 15 | 386417.6283 | 373162.5 | 759580.1283
| 2024-10-01 | 16 | 386417.6283 | 373162.5 | 759580.1283
| 2024-11-01 | 17 | 386417.6283 | 373162.5 | 759580.1283
| 2024-12-01 | 18 | 386417.6283 | 373162.5 | 759580.1283
| 2025-01-01 | 19 | 386417.6283 | 373162.5 | 759580.1283
| 2025-02-01 | 20 | 386417.6283 | 373162.5 | 759580.1283
| 2025-03-01 | 21 | 386417.6283 | 373162.5 | 759580.1283
| 2025-04-01 | 22 | 386417.6283 | 373162.5 | 759580.1283
| 2025-05-01 | 23 | 386417.6283 | 373162.5 | 759580.1283
| 2025-06-01 | 24 | 386417.6283 | 373162.5 | 759580.1283
| 2025-07-01 | 25 | 444380.2725 | 186581.25 | 630961.5225
| 2025-08-01 | 26 | 444380.2725 | 186581.25 | 630961.5225
| 2025-09-01 | 27 | 444380.2725 | 186581.25 | 630961.5225
| 2025-10-01 | 28 | 444380.2725 | 186581.25 | 630961.5225
| 2025-11-01 | 29 | 444380.2725 | 186581.25 | 630961.5225
| 2025-12-01 | 30 | 444380.2725 | 186581.25 | 630961.5225
| 2026-01-01 | 31 | 444380.2725 | 186581.25 | 630961.5225
| 2026-02-01 | 32 | 444380.2725 | 186581.25 | 630961.5225
| 2026-03-01 | 33 | 444380.2725 | 186581.25 | 630961.5225
| 2026-04-01 | 34 | 444380.2725 | 186581.25 | 630961.5225
| 2026-05-01 | 35 | 444380.2725 | 186581.25 | 630961.5225
| 2026-06-01 | 36 | 444380.2725 | 186581.25 | 630961.5225
| 2026-07-01 | 37 | 511037.3133 | 186581.25 | 697618.5633
| 2026-08-01 | 38 | 511037.3133 | 186581.25 | 697618.5633
| 2026-09-01 | 39 | 511037.3133 | 186581.25 | 697618.5633
| 2026-10-01 | 40 | 511037.3133 | 186581.25 | 697618.5633
| 2026-11-01 | 41 | 511037.3133 | 186581.25 | 697618.5633
| 2026-12-01 | 42 | 511037.3133 | 186581.25 | 697618.5633
| 2027-01-01 | 43 | 511037.3133 | 186581.25 | 697618.5633
| 2027-02-01 | 44 | 511037.3133 | 186581.25 | 697618.5633
| 2027-03-01 | 45 | 511037.3133 | 186581.25 | 697618.5633
| 2027-04-01 | 46 | 511037.3133 | 186581.25 | 697618.5633
| 2027-05-01 | 47 | 511037.3133 | 186581.25 | 697618.5633
| 2027-06-01 | 48 | 511037.3133 | 186581.25 | 697618.5633
| 2027-07-01 | 49 | 587692.91 | 186581.25 | 774274.16
| 2027-08-01 | 50 | 587692.91 | 186581.25 | 774274.16
| 2027-09-01 | 51 | 587692.91 | 186581.25 | 774274.16
| 2027-10-01 | 52 | 587692.91 | 186581.25 | 774274.16
| 2027-11-01 | 53 | 587692.91 | 186581.25 | 774274.16
| 2027-12-01 | 54 | 587692.91 | 186581.25 | 774274.16
| 2028-01-01 | 55 | 587692.91 | 186581.25 | 774274.16
| 2028-02-01 | 56 | 587692.91 | 186581.25 | 774274.16
| 2028-03-01 | 57 | 587692.91 | 186581.25 | 774274.16
| 2028-04-01 | 58 | 587692.91 | 186581.25 | 774274.16
| 2028-05-01 | 59 | 587692.91 | 186581.25 | 774274.16
| 2028-06-01 | 60 | 587692.91 | 186581.25 | 774274.16
|  |  | 23154337.49 | 11194875 | 34349212.49

## Mod Hours
Vendor Name: HealthTech Solutions, LLC
YH23-0021 Arizona System Integrator
Estimated Modification Hours Calculation
Total Hours | 90000
Rate | 165.85
Avg Hrs/Mnth
Year 1 | 25% | 22500 | 3731625 | 2500
Year 2 | 30% | 27000 | 4477950 | 2250
Year 3 | 15% | 13500 | 2238975 | 1125
Year 4 | 15% | 13500 | 2238975 | 1125
Year 5 | 15% | 13500 | 2238975 | 1125
14926500

## Fiscal Year Breakdown
Vendor Name: HealthTech Solutions, LLC
YH23-0021 Arizona System Integrator
Estimated Contract Cost by Fiscal Year
Federal Fiscal Year | Amount
2023 | 1617620.7612
2024 | 12906538.1038
2025 | 8729105.7225
2026 | 7771509.3925
2027 | 8601389.55
2028 | 6968467.44
Total | 46594630.97
State Fiscal Year | Total Estimated Cost
2023 | 0
2024 | 12245418.48
2025 | 9114961.54
2026 | 7571538.27
2027 | 8371422.76
2028 | 9291289.92
Total | 46594630.97