## Corporate Compliance Plan-Sampl
To be completed by: |  | [Contractor]
Reporting Period |  | [Quarterly]
Goal: To have all program integrity related policies as required by contract with AHCCCS, updated and properly disseminated to all employees and subcontractors before the end of the 4 QTR.
Date | Elements: | Yes /No? If No Explain | Activities Qtr 1 | % done Qtr 1 | Activities Qtr 2 | % done Qtr 2 | Activities QTR 3 | % done Qtr 3 | Activities Qtr 4 | % done Qtr 4 | Outcomes
| Is there a policy that pertains to Ethics? | YES | Example: Policy under revision: Submit to Compliance committee and officer for review and approval. | 50% | Policy revisions complete, submit to board for review and approval | 75% | Submit to AHCCCS for review and approval | 80% | Policy has been disseminated to all employees and subcontractors as applicable. | 100%
Are enforcement of standards through well-publicized disciplinary guidelines established?
| Is there a policy that pertains to fraud, waste, and abuse identification and reporting? | YES |  | 50% |  | 100% |  | 100% |  | 100%
Have procedures that include the provision for the prompt referral of any potential fraud, waste, or abuse to AHCCCS-OIG been established and implemented to include AHCCCS-OIG contact information?
Does the AHCCCS-OIG contact information include the website, email address, and phone number?
Have policies and proceedures been established that address the Deficit Reduction Act of 2005 (DRA), where Contractors, as a condition for receiving payments shall establish written policies for any employees and of any contractor or agent, detailing of the Social Security Act?
Does the DRA policy address: The Federal False Claims Act provisions; The administrative remedies for false claims and statements; Any State laws relating to civil or criminal penalties for false claims and statements; and The whistleblower protections under such laws?
| Is there a policy that explains the False Claims Act requirements and how is it disseminated? | YES |  | 100% |  | 100% |  | 100% |  | 100%
| Is there a Corporate Compliance Officer and designated Regularory Compliance Committee involving the Board of Directors and the Contractor’s senior management? Functions? Is that effective? | YES |  | 100% |  | 100% |  | 100% |  | 100%
Are there effective lines of communication between the Corporate Compliance Officer and the Contractor’s employees?
| Is the plan ensuring that all program integrity policies are up to date and reflect specific efforts to address FWA? | YES |  | 100% |  | 100% |  | 100% |  | 100%
| Is the compliance plan updated regularly? Is the effectiveness of the program evaluated? | YES |  | 100% |  | 100% |  | 100% |  | 100%
Goal 2: To ensure effective training and education for the Compliance \Officer and all employees including leadership of the organization. (DRA, FCA, Qui Tam and Whistleblower Provisions.)
Date | Elements: | Yes /No? If No, What Steps? | Activities Qtr 1 | % done Qtr 1 | Activities Qtr 2 | % done Qtr 2 | Activities QTR 3 | % done Qtr 3 | Activities Qtr 4 | % done Qtr 4 | Outcomes
| Is there a policy(s) that pertains to training? | YES | Example: The policy is under revision to enforce FWA reporting mechanisms. | 65% | Example: The policy has been approved and has been sent to AHCCCS/OIG prior to be disseminated. | 100% | Example: AHCCCS/OIG has agreed to the policy content. | 100% | Example: The policy has been disseminated accordingly. | 100%
| Is there a curriculum for the courses that will be addressed to meet this goal? | NO |  | 50% |  | 75% |  | 85% |  | 100%
| Is the plan measuring the effectiveness of the training? How? | YES |  | 50% |  | 50% |  | 50% |  | 50%
| Is there a schedule for training? If so, how is the training implemented | YES |  | 100% |  | 100% |  | 100% |  | 100%
| Is the Program Integrity information presented to new employees, current employees, interns, volunteers, and subcontractors? | YES |  | 100% |  | 100% |  | 100% |  | 100%
| Are there multiple ways in which the training information is presented?PPT? CBT? Online? Lecture? | NO |  | 100% |  | 100% |  | 100% |  | 100%
Goal 3: Ensure compliance and proper monitoring in accordance with Federal and AHCCCS contractual requirements for internal and external audits related to Fraud, Waste and Abuse.
Date | Elements: | Yes /No? If No, What Steps? | Activities Qtr 1 | % done Qtr 1 | Activities Qtr 2 | % done Qtr 2 | Activities QTR 3 | % done Qtr 3 | Activities Qtr 4 | % done Qtr 4 | Outcomes
| Is there a provision or system in policy for internal and external audits to include dedicated staff? | YES |  | 100% |  | 100% |  | 100% |  | 100%
Does the external audit policy require an audit plan, schdule and executive summary to be submitted the the AHCCCS-OIG?
Does the provision or system include monitoring and auditing of compliance risks, prompt response to compliance issues, investigation of potential compliance problems as identified in the course of self-evaluation and audits, correction of problems promptly and thoroughly to reduce the potential for recurrence, ongoing compliance with requirements under the Contract, and external monitoring and auditing of subcontractors.
| Is there a methodology or protocol for provider audits? If so, is the Health plan conducting methodical inspections? | YES | Example: the Health plan is contracting with a vendor to conduct periodic audits to all programs. | 100% |  | 100% |  | 100% |  | 100%
| Is the health plan measuring, correcting and preventing overpayments? How? | YES |  | 100% |  | 100% |  | 100% |  | 100%
| What detection activities are conducted? Are those activities generating potential audit cases? | NO | Example: The audit unit is conducting an internal audit to identify potential gaps during the credentialing processes | 0% |  | 50% |  | 85% |  | 100%
Goal 4: The contractor must ensure proper External monitoring/auditing - usage of data and other detection systems
Date | Elements: | Yes /No? If No, What Steps? | Activities Qtr 1 | % done Qtr 1 | Activities Qtr 2 | % done Qtr 2 | Activities QTR 3 | % done Qtr 3 | Activities Qtr 4 | % done Qtr 4 | Outcomes
| Is there a policy that addresses provider audits based on data/algorithms? | YES | Example: the health plan is using a system based on predetermined algorithms that identify high utilization patterns. | 100% |  | 100% |  | 100% |  | 100%
| Specific data mining activities performed? | YES |  | 100% |  | 100% |  | 100% |  | 100%
| Audits are conducted on-site or desk? Explain in either case. | YES |  | 100% |  | 100% |  | 100% |  | 100%
| Is the plan using trend analysis to prioritize auditing activities? If so, how? | NO |  | 100% |  | 100% |  | 100% |  | 100%
| What are the actions taken by the plan according to audit results? | YES |  | 100% |  | 100% |  | 100% |  | 100%
Goal 5: The contractor must ensure Disclosure of Ownership and Control and Disclosure of Information persons convicted of Crime is implemented according to the federal regulation and the contractual provision.
Date | Elements: | Yes /No? If No, What Steps? | Activities Qtr 1 | % done Qtr 1 | Activities Qtr 2 | % done Qtr 2 | Activities QTR 3 | % done Qtr 3 | Activities Qtr 4 | % done Qtr 4 | Outcomes
| Are employees screened against the federal databases when hired and monthly thereafter? | YES |  | 100% |  | 100% |  | 100% |  | 100%
| Are subcontractors, administrative subcontractors, vendors and other entities required to check, identify and report excluded individuals? | NO | Example: No schedule set up for reporting. | 30% | Corp Compliance officer and board meet throughout the qtr to develop a plan for reporting. | 70% | Compliance Officer received information monthly and reports to OIG if an excluded individual is identified. | 100% | Plan goes into effect. New policies and procedures implemented. Compliance Officer gathers results on ongoing basis. | 100%
| Is the credentialing process ensuring that these checks are conducted? | YES |  | 100% |  | 100% |  | 100% |  | 100%
| What other background checks does the plan has incorporated? | YES |  | 100% |  | 100% |  | 100% |  | 100%
Does the Contractor report a description of transactions between the Contractor and a party in interest including the following transactions; Any sale or exchange, or leasing of any property between the organization and such a party; Any furnishing for consideration of goods, services , or facilities between the organization and such a party, but not including salaries paid to employees for services provided in the normal course of their employment; Any lending of money or other extension of credit between the organization and such a party?

## Options (hidden)
YES
NO

## OptionA (hidden)
0%
15%
20%
25%
30%
35%
40%
45%
50%
55%
60%
65%
70%
75%
80%
85%
90%
95%
100%